## Introduction
MDN - Spend Manager Drop 1 Test Plan
Author
Document Version
0.1
Introduction
The Test Plan is designed to describe the scope, resources and schedule of all testing activities. The plan identifies: 1. Items to be tested 2. Features to be tested 3. Types of testing to be performed
Contents - Areas of Testing
Domain system testing for Spend Manager Drop 1 This testing covers MDN aggregation only. Rating, Barring and Notifications are included in the next drop
References
Amdocs Spend Manager HLD v1.0

## Domestic Voice
Test ID | Test Case | Test Objective | Pre condition | Test Steps | expected result | Test Data - CTN | Test Data - BAN | Test data - Source system | Test Data - Priceplan Type | Test Data - Priceplan | Test Data - SOCs | Test Data - rollover day | TIL stub | Result
1 | UK call to a Vodafone Mobile | Confirm usage is aggregated to the correct Call Category | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Tariff Class of 501 using record type 32 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 10006 | 7701000001 | 123000001 | CG | VBP_16GB | 1NETHDB16 |  | 1 | Yes
2 | UK call to another UK network | Confirm usage is aggregated to the correct Call Category | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Tariff Class of 525 using record type 64 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 10007 | 7701000002 | 123000002 | CG | EBU9_RS0_DS | 1NETBPVUH |  | 1 | Yes
3 | UK call to an NGCS number | Confirm usage is aggregated to the correct Call Category | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call to 0913620620 with Tariff Class of 525 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 10018 using tariff class 8929 | 7701000003 | 123000003 | CG | EBU_1NET_PPM_1 | 1NETPC60P |  | 1 | Yes
4 | UK on-VPN call | Confirm usage is aggregated to the correct Call Category | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Tariff Class of 584 using record type 32 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 10012 | 7701000004 | 123000004 | CG | CBU13_5GB | 1O5O5GLZ |  | 1 | Yes
5 | UK call to a voice shortcode | Confirm usage is aggregated to the correct Call Category | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Tariff Class of 588using record type 32 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 10023 | 7701000005 | 123000005 | CG | CBU13_5GB | 1O5O5GLZ |  | 1 | Yes
6 | UK call to a Free destination | Confirm usage is aggregated to the correct Call Category | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Tariff Class of 624 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 10003 | 7701000006 | 123000006 | CG | EBU9_RS2_DS | BUADTB02 |  | 1 | Yes
7 | Aggregation of multiple calls to a call ctegory | Confirm multiple calls are aggregated to the same Call Category | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Tariff Class of 501 3. Generate a 40 second call with Tariff Class of 502 4. View the usage aggregation via the MDN web Client | A total of 100 seconds is aggregated to MDN call category 10006 | 7701000007 | 123000007 | CG | EBU9_RS2_DS | BUADTB02 |  | 1 | Yes
8 | Aggregation re-set over a month end | Confirm usage is aggregated to the correct Call Category | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Tariff Class of 501 3. View the usage aggregation via the MDN web Client | The aggregation for MDN call category 10006 is zero at the start of the next bill month | 7701000008 | 123000008 | CG | CBU13_32GB | LENX32GBZ |  | 25 | Yes
9 | UK call to another UK network using an MNP B number | Confirm usage is aggregated to the correct Call Category and Tariff Class is swapped | MSISDN is connected to a SM eligible price plan Called number is showing as ported out in the MNP lookup | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Tariff Class of 501 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 10007 | 7701000009 | 123000009 | CG | PS_2017_3GB | PIV3G36 |  | 1 | Yes
10 | UK call to a Vodafone mobile using an MNP B number | Confirm usage is aggregated to the correct Call Category and Tariff Class is swapped | MSISDN is connected to a SM eligible price plan Called number is showing as ported in in the MNP lookup | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Tariff Class of 525 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 10006 | 7701000010 | 123000010 | CG | EBUL_250MB_BT | VBF4INV |  | 1 | Yes
11 | b number for UK voice calls | Confirm the B - number is not used in aggregation for domestic voice | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Tariff Class of 501 and b-number of 001260123456 (USA) 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 10006 for domestic calls to a VF mobile. The b-number is ignored | 7701000011 | 123000011 | CG | BUSOPT8 | VBODV5 |  | 1 | Yes
12 | b number formatting | Confirm that b-numbers with incorrect characters are procssed | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Tariff Class of 501 and b-number of *#7878123456 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 10006 | 7701000012 | 123000012 | CG | EBUL_250MB_BT | VBUSF12 |  | 1 | Yes

## Domestic SMS
Test ID | Test Case | Test Objective | Pre condition | Test Steps | expected result | Test Data - CTN | Test Data - BAN | Test data - Source system | Test Data - Priceplan Type | Test Data - Priceplan | Test Data - SOCs | Test Data - rollover day | TIL stub | Result
13 | UK SMS to a Vodafone Mobile | Confirm the SMS is aggregated to the correct Call Category | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate an MO SMS with GSM Service 177500 3. View the usage aggregation via the MDN web Client | The SMS is aggregated to MDN call category 30028 | 7701000013 | 123000013 | LG | VBP_16GB | 1NETHDB16 |  | 1 | Yes
14 | UK MO premium rate SMS | Confirm the SMS is aggregated to the correct Call Category | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate an MO SMS with GSM Service 600790 3. View the usage aggregation via the MDN web Client | The SMS is aggregated to MDN call category 30035 | 7701000014 | 123000014 | LG | EBU9_RS0_DS | 1NETBPVUH |  | 1 | Yes
15 | UK MT premium rate SMS | Confirm the SMS is aggregated to the correct Call Category | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate an MT SMS with GSM Service 724700 3. View the usage aggregation via the MDN web Client | The SMS is aggregated to MDN call category 30056 | 7701000015 | 123000015 | LG | EBU_1NET_PPM_1 | 1NETPC60P |  | 1 | Yes
16 | UK leg of an interntional SMS - worldwide | Confirm the SMS is aggregated to the correct Call Category | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate an SMS with GSM Service 677700 3. View the usage aggregation via the MDN web Client | The SMS is aggregated to MDN call category 30023 | 7701000016 | 123000016 | LG | CBU13_5GB | 1O5O5GLZ |  | 1 | Yes
17 | UK leg of an interntional SMS - Europe | Confirm the SMS is aggregated to the correct Call Category | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate an SMS with GSM Service 737700 3. View the usage aggregation via the MDN web Client | The SMS is aggregated to MDN call category 30064 | 7701000017 | 123000017 | LG | CBU13_5GB | 1O5O5GLZ |  | 1 | Yes
18 | UK leg of an interntional SMS - Channel Islands | Confirm the SMS is aggregated to the correct Call Category | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate an SMS with GSM Service 695700 3. View the usage aggregation via the MDN web Client | The SMS is aggregated to MDN call category 30024 | 7701000018 | 123000018 | LG | EBU9_RS2_DS | BUADTB02 |  | 1 | Yes
19 | UK SMS to a Free destination | Confirm the SMS is aggregated to the correct Call Category | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate an SMS with GSM Service 607700 3. View the usage aggregation via the MDN web Client | The SMS is aggregated to MDN call category 30004 | 7701000019 | 123000019 | LG | EBU9_RS2_DS | BUADTB02 |  | 1 | Yes
20 | Aggregation of multiple SMS to a call ctegory | Confirm the SMS is aggregated to the correct Call Category | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate 5 SMS with GSM Service 177500, generate 3 SMS with GSM service 707700 3. View the usage aggregation via the MDN web Client | Three SMS are aggregated to MDN call category 30004 Five SMS are aggregated to category 30028 | 7701000020 | 123000020 | LG | CBU13_32GB | LENX32GBZ |  | 1 | Yes
21 | SMS Aggregation re-set over a month end | Confirm the SMS is aggregated to the correct Call Category | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate an MO SMS with GSM Service 177500 3. View the usage aggregation via the MDN web Client | Aaggregation to MDN call category 30028 is zero on the first day of the next month | 7701000021 | 123000021 | LG | PS_2017_3GB | PIV3G36 |  | 25 | Yes
22 | b number for UK SMS | Confirm the B - number is not used in aggregation for domestic SMS | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate an MO SMS with GSM Service 177500 and b-number of 001260123456 (USA) 3. View the usage aggregation via the MDN web Client | The SMS is aggregated to UK SMS MDN call category 30028, not as an international call | 7701000022 | 123000022 | LG | EBUL_250MB_BT | VBF4INV |  | 1 | Yes

## MMS
Test ID | Test Case | Test Objective | Pre condition | Test Steps | expected result | Test Data - CTN | Test Data - BAN | Test data - Source system | Test Data - Priceplan Type | Test Data - Priceplan | Test Data - SOCs | Test Data - rollover day | TIL stub | Result
23 | UK MMS text | Confirm that the MMS is aggregated to the correct MDN call category | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate an MMS CDR with Tariff Class 4005 and Network of Call Origin GBR 3. View the usage aggregation via the MDN web Client | The MMS is aggregated to MDN Call Category 20001 | 7701000023 | 123000023 | CG | VBP_16GB | 1NETHDB16 |  | 1 | Yes
24 | UK MMS picture | Confirm that the MMS is aggregated to the correct MDN call category | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate an MMS CDR with Tariff Class 4010 and Network of Call Origin GBR 3. View the usage aggregation via the MDN web Client | The MMS is aggregated to MDN Call Category 20002 | 7701000024 | 123000024 | CG | EBU9_RS0_DS | 1NETBPVUH |  | 1 | Yes
25 | UK MMS video | Confirm that the MMS is aggregated to the correct MDN call category | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate an MMS CDR with Tariff Class 4015 and Network of Call Origin GBR 3. View the usage aggregation via the MDN web Client | The MMS is aggregated to MDN Call Category 20003 | 7701000025 | 123000025 | CG | EBU_1NET_PPM_1 | 1NETPC60P |  | 1 | Yes
26 | Roaming MMS text - Europe | Confirm that the MMS is aggregated to the correct MDN call category | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate an MMS CDR with Tariff Class 4005 and Network of Call Origin BEL TB 3. View the usage aggregation via the MDN web Client | The MMS is aggregated to MDN Call Category 20005 | 7701000026 | 123000026 | CG | CBU13_5GB | 1O5O5GLZ |  | 1 | Yes
27 | Roaming MMS picture - europe | Confirm that the MMS is aggregated to the correct MDN call category | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate an MMS CDR with Tariff Class 4010 and Network of Call Origin BEL TB 3. View the usage aggregation via the MDN web Client | The MMS is aggregated to MDN Call Category 20026 | 7701000027 | 123000027 | CG | CBU13_5GB | 1O5O5GLZ |  | 1 | Yes
28 | Roaming MMS video - europe | Confirm that the MMS is aggregated to the correct MDN call category | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate an MMS CDR with Tariff Class 4015 and Network of Call Origin BEL TB 3. View the usage aggregation via the MDN web Client | The MMS is aggregated to MDN Call Category 20047 | 7701000028 | 123000028 | CG | EBU9_RS2_DS | BUADTB02 |  | 1 | Yes
29 | Roaming MMS text - USA | Confirm that the MMS is aggregated to the correct MDN call category | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate an MMS CDR with Tariff Class 4005 and Network of Call Origin USA NC 3. View the usage aggregation via the MDN web Client | The MMS is aggregated to MDN Call Category 20024 | 7701000029 | 123000029 | CG | EBU9_RS2_DS | BUADTB02 |  | 1 | Yes
30 | Roaming MMS picture - USA | Confirm that the MMS is aggregated to the correct MDN call category | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate an MMS CDR with Tariff Class 4010 and Network of Call Origin USA NC 3. View the usage aggregation via the MDN web Client | The MMS is aggregated to MDN Call Category 20045 | 7701000030 | 123000030 | CG | CBU13_32GB | LENX32GBZ |  | 1 | Yes
31 | Roaming MMS video - USA | Confirm that the MMS is aggregated to the correct MDN call category | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate an MMS CDR with Tariff Class 4015 and Network of Call Origin USA NC 3. View the usage aggregation via the MDN web Client | The MMS is aggregated to MDN Call Category 20066 | 7701000031 | 123000031 | CG | PS_2017_3GB | PIV3G36 |  | 1 | Yes
32 | Roaming MMS text - Australia | Confirm that the MMS is aggregated to the correct MDN call category | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate an MMS CDR with Tariff Class 4005 and Network of Call Origin AUS VF 3. View the usage aggregation via the MDN web Client | The MMS is aggregated to MDN Call Category 20023 | 7701000032 | 123000032 | CG | EBUL_250MB_BT | VBF4INV |  | 1 | Yes
33 | Roaming MMS picture - Australia | Confirm that the MMS is aggregated to the correct MDN call category | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate an MMS CDR with Tariff Class 4010 and Network of Call Origin AUS VF 3. View the usage aggregation via the MDN web Client | The MMS is aggregated to MDN Call Category 20044 | 7701000033 | 123000033 | CG | BUSOPT8 | VBODV5 |  | 1 | Yes
34 | Roaming MMS video - Australia | Confirm that the MMS is aggregated to the correct MDN call category | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate an MMS CDR with Tariff Class 4015 and Network of Call Origin AUD VF 3. View the usage aggregation via the MDN web Client | The MMS is aggregated to MDN Call Category 20065 | 7701000034 | 123000034 | CG | EBUL_250MB_BT | VBUSF12 |  | 1 | Yes

## International voice
Test ID | Test Case | Test Objective | Pre condition | Test Steps | expected result | Test Data - CTN | Test Data - BAN | Test data - Source system | Test Data - Priceplan Type | Test Data - Priceplan | Test Data - SOCs | Test Data - rollover day | TIL stub | Result
35 | Calls from UK to MDN zone Europe_1a_Cfree | Confirm that international voice calls are aggregated to the correct MDN call category | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Tariff Class of 509 and B number with prefix or 00262 (France Reunion) 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 40002 | 7701000035 | 123000035 | CG | VBP_16GB | 1NETHDB16 |  | 1 | Yes
36 | Calls from UK to MDN zone Europe_1_Cfree | Confirm that international voice calls are aggregated to the correct MDN call category | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Tariff Class of 509 and B number with prefix or 0033 (France) 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 40003 | 7701000036 | 123000036 | CG | EBU9_RS0_DS | 1NETBPVUH |  | 1 | Yes
37 | Calls from UK to MDN zone Europe_2_Cfur | Confirm that international voice calls are aggregated to the correct MDN call category | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Tariff Class of 510 and B number with prefix or 00355 (Albania) 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 40005 | 7701000037 | 123000037 | CG | EBU_1NET_PPM_1 | 1NETPC60P |  | 1 | Yes
38 | Calls from UK to MDN zone Europe_2b_Cfree | Confirm that international voice calls are aggregated to the correct MDN call category | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Tariff Class of 510 and B number with prefix or 0090 (Turkey) 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 40006 | 7701000038 | 123000038 | CG | CBU13_5GB | 1O5O5GLZ |  | 1 | Yes
39 | Calls from UK to MDN zone ROW_Cfur | Confirm that international voice calls are aggregated to the correct MDN call category | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Tariff Class of 512 and B number with prefix or 00965 (Kuwait) 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 40009 | 7701000039 | 123000039 | CG | CBU13_5GB | 1O5O5GLZ |  | 1 | Yes
40 | Calls from UK to MDN zone ROW_C4 | Confirm that international voice calls are aggregated to the correct MDN call category | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Tariff Class of 764 and B number with prefix or 00252 (Somalia) 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 40016 | 7701000040 | 123000040 | CG | EBU9_RS2_DS | BUADTB02 |  | 1 | Yes
41 | Calls from UK to MDN zone ROW_C1 | Confirm that international voice calls are aggregated to the correct MDN call category | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Tariff Class of 514 and B number with prefix or 00964 (Iraq) 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 40010 | 7701000041 | 123000041 | CG | EBU9_RS2_DS | BUADTB02 |  | 1 | Yes
42 | Calls from UK to MDN zone ROW_C2 | Confirm that international voice calls are aggregated to the correct MDN call category | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Tariff Class of 514 and B number with prefix or 00221 (Senegal) 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 40011 | 7701000042 | 123000042 | CG | CBU13_32GB | LENX32GBZ |  | 1 | Yes
43 | Calls from UK to MDN zone ROW_C3 | Confirm that international voice calls are aggregated to the correct MDN call category | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Tariff Class of 515 and B number with prefix or 00216 (Tunisia) 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 40015 | 7701000043 | 123000043 | CG | PS_2017_3GB | PIV3G36 |  | 1 | Yes
44 | Calls from UK to MDN zone Taiwan | Confirm that international voice calls are aggregated to the correct MDN call category | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Tariff Class of 687 and B number with prefix or 00886 (Taiwan) 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 40021 | 7701000044 | 123000044 | CG | EBUL_250MB_BT | VBF4INV |  | 1 | Yes
45 | Calls from UK to MDN zone Andorra | Confirm that international voice calls are aggregated to the correct MDN call category | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Tariff Class of 509 and B number with prefix or 00376 (Andorra) 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 40005 | 7701000045 | 123000045 | CG | BUSOPT8 | VBODV5 |  | 1 | Yes
46 | Calls from UK to MDN zone ROW2C4 | Confirm that international voice calls are aggregated to the correct MDN call category | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Tariff Class of 514 and B number with prefix or 00251 (Ethiopia) 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 40012 | 7701000046 | 123000046 | CG | EBUL_250MB_BT | VBUSF12 |  | 1 | Yes
47 | Calls from UK to MDN zone ROW2C1 | Confirm that international voice calls are aggregated to the correct MDN call category | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Tariff Class of 515 and B number with prefix or 00261 (Madagascar) 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 40017 | 7701000047 | 123000047 | CG | VBV_1GB | VBVHX1G |  | 1 | Yes
48 | Calls from UK to MDN zone ROW2_Cfur | Confirm that international voice calls are aggregated to the correct MDN call category | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Tariff Class of 515 and B number with prefix or 00504 (Honduras) 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 40013 | 7701000048 | 123000048 | CG | EBUL_250MB_BT | VBF9INV |  | 1 | Yes
49 | Calls from UK to MDN zone ROW2C3 | Confirm that international voice calls are aggregated to the correct MDN call category | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Tariff Class of 515 and B number with prefix or 001758 (St Lucia) 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 40019 | 7701000049 | 123000049 | CG | BUSOPT12 | VBODV1 |  | 1 | Yes
50 | Calls from UK to MDN zone EC_further | Confirm that international voice calls are aggregated to the correct MDN call category | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Tariff Class of 515 and B number with prefix or 0055 (Brazil) 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 40008 | 7701000050 | 123000050 | CG | PS_2017_2GB | PSE0GB2M |  | 1 | Yes

## Roaming Voice
Test ID | Test Case | Test Objective | Pre condition | Test Steps | expected result | Test Data - CTN | Test Data - BAN | Test data - Source system | Test Data - Priceplan Type | Test Data - Priceplan | Test Data - SOCs | Test Data - rollover day | TIL stub | Result
51 | Roaming calls from Europe_1_Cfree to Europe_2_Cfur | Confirm that roaming voice calls are aggregated to the correct MDN call category based on Network of Call origin and B Number | MSISDN is connected to a SM eligible price plan without Business Traveller | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Network of Call Origin DEU and B number with prefix or 00355 (ALB) 3. View the usage aggregation via the MDN web Client " | The 60 second call is aggregated to MDN call category 50028 | 7701000051 | 123000051 | CG | EBU9_RS0_DS | 1NETBPVUH |  | 1 | Yes
52 | Roaming calls from Europe_1_Cfree to Europe_2b_Cfree | Confirm that roaming voice calls are aggregated to the correct MDN call category based on Network of Call origin and B Number | MSISDN is connected to a SM eligible price plan without Business Traveller | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Network of Call Origin DEU and B number with prefix or 0090 (TUR) 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 50029 | 7701000052 | 123000052 | CG | EBU9_RS0_DS | 1NETBPVUH |  | 1 | Yes
53 | Roaming calls from Europe_1_Cfree to ROW_Cfur | Confirm that roaming voice calls are aggregated to the correct MDN call category based on Network of Call origin and B Number | MSISDN is connected to a SM eligible price plan without Business Traveller | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Network of Call Origin DEU and B number with prefix or 00880 (BGD) 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 50032 | 7701000053 | 123000053 | CG | EBU_1NET_PPM_1 | 1NETPC60P |  | 1 | Yes
54 | Roaming calls from Europe_1_Cfree to ROW_C4 | Confirm that roaming voice calls are aggregated to the correct MDN call category based on Network of Call origin and B Number | MSISDN is connected to a SM eligible price plan without Business Traveller | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Network of Call Origin DEU and B number with prefix or 00963 (Syria) 3. View the usage aggregation via the MDN web Client " | The 60 second call is aggregated to MDN call category 50033 | 7701000054 | 123000054 | CG | EBU9_RS2_DS | BUADTB02 |  | 1 | Yes
55 | Roaming calls from Europe_1_Cfree to ROW_C1 | Confirm that roaming voice calls are aggregated to the correct MDN call category based on Network of Call origin and B Number | MSISDN is connected to a SM eligible price plan without Business Traveller | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Network of Call Origin DEU and B number with prefix or 00250 (Rwanda) 3. View the usage aggregation via the MDN web Client " | The 60 second call is aggregated to MDN call category 50034 | 7701000055 | 123000055 | CG | EBU9_RS2_DS | BUADTB02 |  | 1 | Yes
56 | Roaming calls from Europe_1_Cfree to ROW_C2 | Confirm that roaming voice calls are aggregated to the correct MDN call category based on Network of Call origin and B Number | MSISDN is connected to a SM eligible price plan without Business Traveller | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Network of Call Origin DEU and B number with prefix or 00263 (Zimbabwe) 3. View the usage aggregation via the MDN web Client " | The 60 second call is aggregated to MDN call category 50035 | 7701000056 | 123000056 | CG | PS_2017_3GB | PIV3G36 |  | 1 | Yes
57 | Roaming calls from Europe_1_Cfree to ROW_C3 | Confirm that roaming voice calls are aggregated to the correct MDN call category based on Network of Call origin and B Number | MSISDN is connected to a SM eligible price plan without Business Traveller | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Network of Call Origin DEU and B number with prefix or 00264 (Namibia) 3. View the usage aggregation via the MDN web Client " | The 60 second call is aggregated to MDN call category 50037 | 7701000057 | 123000057 | CG | EBUL_250MB_BT | VBF4INV |  | 1 | Yes
58 | Roaming calls from Europe_1_Cfree to Taiwan | Confirm that roaming voice calls are aggregated to the correct MDN call category based on Network of Call origin and B Number | MSISDN is connected to a SM eligible price plan without Business Traveller | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Network of Call Origin DEU and B number with prefix or 00886 (Taiwan) 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 50038 | 7701000058 | 123000058 | CG | BUSOPT8 | VBODV5 |  | 1 | Yes
59 | Roaming calls from Europe_1_Cfree to Andorra | Confirm that roaming voice calls are aggregated to the correct MDN call category based on Network of Call origin and B Number | MSISDN is connected to a SM eligible price plan without Business Traveller | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Network of Call Origin DEU and B number with prefix or 00376 (Andorra) 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 50039 | 7701000059 | 123000059 | CG | EBUL_250MB_BT | VBUSF12 |  | 1 | Yes
60 | Roaming calls from Europe_1_Cfree to ROW2C4 | Confirm that roaming voice calls are aggregated to the correct MDN call category based on Network of Call origin and B Number | MSISDN is connected to a SM eligible price plan without Business Traveller | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Network of Call Origin DEU and B number with prefix or 00251 (Ethiopia) 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 50040 | 7701000060 | 123000060 | CG | EBUL_250MB_BT | VBUSF12 |  | 1 | Yes
61 | Roaming calls from Europe_1_Cfree to ROW2C1 | Confirm that roaming voice calls are aggregated to the correct MDN call category based on Network of Call origin and B Number | MSISDN is connected to a SM eligible price plan without Business Traveller | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Network of Call Origin DEU and B number with prefix or 00975 (Bhutan) 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 50041 | 7701000061 | 123000061 | CG | EBUL_250MB_BT | VBF9INV |  | 1 | Yes
62 | Roaming calls from Europe_1_Cfree to ROW2_Cfur | Confirm that roaming voice calls are aggregated to the correct MDN call category based on Network of Call origin and B Number | MSISDN is connected to a SM eligible price plan without Business Traveller | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Network of Call Origin DEU and B number with prefix or 00998 (Uzbekistan) 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 50042 | 7701000062 | 123000062 | CG | BUSOPT12 | VBODV1 |  | 1 | Yes
63 | Roaming calls from Europe_1_Cfree to ROW2C3 | Confirm that roaming voice calls are aggregated to the correct MDN call category based on Network of Call origin and B Number | MSISDN is connected to a SM eligible price plan without Business Traveller | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Network of Call Origin DEU and B number with prefix or 001758 (St Lucia) 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 50043 | 7701000063 | 123000063 | CG | PS_2017_2GB | PSE0GB2M |  | 1 | Yes
64 | Roaming calls from Europe_1_Cfree to EC_further | Confirm that roaming voice calls are aggregated to the correct MDN call category based on Network of Call origin and B Number | MSISDN is connected to a SM eligible price plan without Business Traveller | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Network of Call Origin DEU and B number with prefix or 0057 (Columbia) 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 50044 | 7701000064 | 123000064 | CG | PS_2017_2GB | PSE0GB2M |  | 1 | Yes
65 | Roaming calls from Europe_1_Cfree to aisa_pacific_Cfur | Confirm that roaming voice calls are aggregated to the correct MDN call category based on Network of Call origin and B Number | MSISDN is connected to a SM eligible price plan without Business Traveller | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Network of Call Origin DEU and B number with prefix or 0064 (New Zealand) 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 50045 | 7701000065 | 123000065 | CG | EBU9_RS0_DS | 1NETBPVUH |  | 1 | Yes
66 | Roaming calls from Europe_1_Cfree to usa_canada_Cfur | Confirm that roaming voice calls are aggregated to the correct MDN call category based on Network of Call origin and B Number | MSISDN is connected to a SM eligible price plan without Business Traveller | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Network of Call Origin DEU and B number with prefix or 001403 (Canada) 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 50046 | 7701000066 | 123000066 | CG | EBU_1NET_PPM_1 | 1NETPC60P |  | 1 | Yes
67 | Roaming calls in country EC_further | Confirm that roaming voice calls are aggregated to the correct MDN call category based on Network of Call origin and B Number | MSISDN is connected to a SM eligible price plan without Business Traveller | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Network of Call Origin JPN and B number with prefix or 0081 (Japan) 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 50415 | 7701000067 | 123000067 | CG | EBU9_RS2_DS | BUADTB02 |  | 1 | Yes
68 | Roaming calls back to the UK EC_further | Confirm that roaming voice calls are aggregated to the correct MDN call category based on Network of Call origin and B Number | MSISDN is connected to a SM eligible price plan without Business Traveller | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Network of Call Origin JPN and B number with prefix or 0044 (UK) 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 50416 | 7701000068 | 123000068 | CG | EBU9_RS2_DS | BUADTB02 |  | 1 | Yes
69 | Roaming calls from EC_further to EC_further | Confirm that roaming voice calls are aggregated to the correct MDN call category based on Network of Call origin and B Number | MSISDN is connected to a SM eligible price plan without Business Traveller | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Network of Call Origin JPN and B number with prefix or 0057 (Columbia) 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 50417 | 7701000069 | 123000069 | CG | PS_2017_3GB | PIV3G36 |  | 1 | Yes
70 | Roaming calls from EC_further to Europe_1a_Cfree | Confirm that roaming voice calls are aggregated to the correct MDN call category based on Network of Call origin and B Number | MSISDN is connected to a SM eligible price plan without Business Traveller | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Network of Call Origin JPN and B number with prefix or 00262 (REU) 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 50418 | 7701000070 | 123000070 | CG | EBUL_250MB_BT | VBF4INV |  | 1 | Yes
71 | Roaming calls from EC_further to Europe_1_Cfree | Confirm that roaming voice calls are aggregated to the correct MDN call category based on Network of Call origin and B Number | MSISDN is connected to a SM eligible price plan without Business Traveller | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Network of Call Origin JPN and B number with prefix or 0049 (Germany) using record type 50 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 50419 | 7701000071 | 123000071 | CG | BUSOPT8 | VBODV5 |  | 1 | Yes
72 | Roaming calls from EC_further to Europe_2_Cfur | Confirm that roaming voice calls are aggregated to the correct MDN call category based on Network of Call origin and B Number | MSISDN is connected to a SM eligible price plan without Business Traveller | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Network of Call Origin JPN and B number with prefix or 00355 (ALB) using record type 50 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 50420 | 7701000072 | 123000072 | CG | EBUL_250MB_BT | VBUSF12 |  | 1 | Yes
73 | Roaming calls from EC_further to Europe_2b_Cfree | Confirm that roaming voice calls are aggregated to the correct MDN call category based on Network of Call origin and B Number | MSISDN is connected to a SM eligible price plan without Business Traveller | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Network of Call Origin JPN and B number with prefix or 0090 (TUR) using record type 50 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 50421 | 7701000073 | 123000073 | CG | EBUL_250MB_BT | VBF4INV |  | 1 | Yes
74 | Roaming calls from EC_further to ROW_Cfur | Confirm that roaming voice calls are aggregated to the correct MDN call category based on Network of Call origin and B Number | MSISDN is connected to a SM eligible price plan without Business Traveller | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Network of Call Origin JPN and B number with prefix or 00880 (BGD) using record type 50 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 50424 | 7701000074 | 123000074 | CG | EBUL_250MB_BT | VBF9INV |  | 1 | Yes
75 | Roaming calls from EC_further to ROW_C4 | Confirm that roaming voice calls are aggregated to the correct MDN call category based on Network of Call origin and B Number | MSISDN is connected to a SM eligible price plan without Business Traveller | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Network of Call Origin JPN and B number with prefix or 00963 (Syria) using record type 50 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 50425 | 7701000075 | 123000075 | CG | BUSOPT12 | VBODV1 |  | 1 | Yes
76 | Roaming calls from EC_further to ROW_C1 | Confirm that roaming voice calls are aggregated to the correct MDN call category based on Network of Call origin and B Number | MSISDN is connected to a SM eligible price plan without Business Traveller | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Network of Call Origin JPN and B number with prefix or 00250 (Rwanda) using record type 50 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 50426 | 7701000076 | 123000076 | CG | PS_2017_2GB | PSE0GB2M |  | 1 | Yes
77 | Roaming calls from EC_further to ROW_C2 | Confirm that roaming voice calls are aggregated to the correct MDN call category based on Network of Call origin and B Number | MSISDN is connected to a SM eligible price plan without Business Traveller | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Network of Call Origin JPN and B number with prefix or 00263 (Zimbabwe) 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 50427 | 7701000077 | 123000077 | CG | PS_2017_2GB | PSE0GB2M |  | 1 | Yes
78 | Roaming calls from EC_further to ROW_C3 | Confirm that roaming voice calls are aggregated to the correct MDN call category based on Network of Call origin and B Number | MSISDN is connected to a SM eligible price plan without Business Traveller | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Network of Call Origin JPN and B number with prefix or 00264 (Namibia) 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 50429 | 7701000078 | 123000078 | CG | EBU9_RS0_DS | 1NETBPVUH |  | 1 | Yes
79 | Roaming calls from EC_further to Taiwan | Confirm that roaming voice calls are aggregated to the correct MDN call category based on Network of Call origin and B Number | MSISDN is connected to a SM eligible price plan without Business Traveller | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Network of Call Origin JPN and B number with prefix or 00886 (Taiwan) 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 50430 | 7701000079 | 123000079 | CG | EBU_1NET_PPM_1 | 1NETPC60P |  | 1 | Yes
80 | Roaming calls from EC_further to Andorra | Confirm that roaming voice calls are aggregated to the correct MDN call category based on Network of Call origin and B Number | MSISDN is connected to a SM eligible price plan without Business Traveller | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Network of Call Origin JPN and B number with prefix or 00376 (Andorra) 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 50431 | 7701000080 | 123000080 | CG | EBU9_RS2_DS | BUADTB02 |  | 1 | Yes
81 | Roaming calls from EC_further to ROW2C4 | Confirm that roaming voice calls are aggregated to the correct MDN call category based on Network of Call origin and B Number | MSISDN is connected to a SM eligible price plan without Business Traveller | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Network of Call Origin JPN and B number with prefix or 00251 (Ethiopia) 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 50432 | 7701000081 | 123000081 | CG | EBU9_RS2_DS | BUADTB02 |  | 1 | Yes
82 | Roaming calls from EC_further to ROW2C1 | Confirm that roaming voice calls are aggregated to the correct MDN call category based on Network of Call origin and B Number | MSISDN is connected to a SM eligible price plan without Business Traveller | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Network of Call Origin JPN and B number with prefix or 00975 (Bhutan) 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 50433 | 7701000082 | 123000082 | CG | EBUL_250MB_BT | VBF4INV |  | 1 | Yes
83 | Roaming calls from EC_further to ROW2_Cfur | Confirm that roaming voice calls are aggregated to the correct MDN call category based on Network of Call origin and B Number | MSISDN is connected to a SM eligible price plan without Business Traveller | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Network of Call Origin JPN and B number with prefix or 00998 (Uzbekistan) 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 50434 | 7701000083 | 123000083 | CG | EBUL_250MB_BT | VBF4INV |  | 1 | Yes
84 | Roaming calls from EC_further to ROW2C3 | Confirm that roaming voice calls are aggregated to the correct MDN call category based on Network of Call origin and B Number | MSISDN is connected to a SM eligible price plan without Business Traveller | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Network of Call Origin JPN and B number with prefix or 001758 (St Lucia) 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 50435 | 7701000084 | 123000084 | CG | BUSOPT8 | VBODV5 |  | 1 | Yes
85 | Roaming calls from EC_further to asia_pacific_Cfur | Confirm that roaming voice calls are aggregated to the correct MDN call category based on Network of Call origin and B Number | MSISDN is connected to a SM eligible price plan without Business Traveller | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Network of Call Origin JPN and B number with prefix or 0064 (New Zealand) 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 50436 | 7701000085 | 123000085 | CG | EBUL_250MB_BT | VBUSF12 |  | 1 | Yes
86 | Roaming calls from EC_further to usa_canada_Cfur | Confirm that roaming voice calls are aggregated to the correct MDN call category based on Network of Call origin and B Number | MSISDN is connected to a SM eligible price plan without Business Traveller | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Network of Call Origin JPN and B number with prefix or 001403 (Canada) 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 50437 | 7701000086 | 123000086 | CG | BUSOPT8 | VBODV5 |  | 1 | Yes
87 | Receiving Calls in Europe_1a_Cfree | Confirm that roaming voice calls are aggregated to the correct MDN call category based on Network of Call origin and B Number | MSISDN is connected to a SM eligible price plan without Business Traveller | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Network of Call Origin REU and record type 51 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 50844 | 7701000087 | 123000087 | CG | EBUL_250MB_BT | VBF9INV |  | 1 | Yes
88 | Receiving Calls in Europe_1_Cfree | Confirm that roaming voice calls are aggregated to the correct MDN call category based on Network of Call origin and B Number | MSISDN is connected to a SM eligible price plan without Business Traveller | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Network of Call Origin DEU and record type 51 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 50845 | 7701000088 | 123000088 | CG | BUSOPT12 | VBODV1 |  | 1 | Yes
89 | Receiving Calls in Europe_2_Cfur | Confirm that roaming voice calls are aggregated to the correct MDN call category based on Network of Call origin and B Number | MSISDN is connected to a SM eligible price plan without Business Traveller | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Network of Call Origin ALB and record type 51 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 50846 | 7701000089 | 123000089 | CG | PS_2017_2GB | PSE0GB2M |  | 1 | Yes
90 | Receiving Calls in Europe_2b_Cfree | Confirm that roaming voice calls are aggregated to the correct MDN call category based on Network of Call origin and B Number | MSISDN is connected to a SM eligible price plan without Business Traveller | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Network of Call Origin TUR and record type 51 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 50847 | 7701000090 | 123000090 | CG | EBU9_RS0_DS | 1NETBPVUH |  | 1 | Yes
91 | Receiving Calls in ROW_Cfur | Confirm that roaming voice calls are aggregated to the correct MDN call category based on Network of Call origin and B Number | MSISDN is connected to a SM eligible price plan without Business Traveller | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Network of Call Origin BGD and record type 51 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 50850 | 7701000091 | 123000091 | CG | EBU9_RS0_DS | 1NETBPVUH |  | 1 | Yes
92 | Receiving Calls in ROW_C4 | Confirm that roaming voice calls are aggregated to the correct MDN call category based on Network of Call origin and B Number | MSISDN is connected to a SM eligible price plan without Business Traveller | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Network of Call Origin SYR and record type 51 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 50851 | 7701000092 | 123000092 | CG | EBU_1NET_PPM_1 | 1NETPC60P |  | 1 | Yes
93 | Receiving Calls in ROW_C1 | Confirm that roaming voice calls are aggregated to the correct MDN call category based on Network of Call origin and B Number | MSISDN is connected to a SM eligible price plan without Business Traveller | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Network of Call Origin RWA and record type 51 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 50852 | 7701000093 | 123000093 | CG | EBU9_RS2_DS | BUADTB02 |  | 1 | Yes
94 | Receiving Calls in ROW_C2 | Confirm that roaming voice calls are aggregated to the correct MDN call category based on Network of Call origin and B Number | MSISDN is connected to a SM eligible price plan without Business Traveller | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Network of Call Origin ZWE and record type 51 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 50853 | 7701000094 | 123000094 | CG | EBU9_RS2_DS | BUADTB02 |  | 1 | Yes
95 | Receiving Calls in ROW_C3 | Confirm that roaming voice calls are aggregated to the correct MDN call category based on Network of Call origin and B Number | MSISDN is connected to a SM eligible price plan without Business Traveller | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Network of Call Origin NAM and record type 51 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 50854 | 7701000095 | 123000095 | CG | PS_2017_3GB | PIV3G36 |  | 1 | Yes
96 | Receiving Calls in Taiwan | Confirm that roaming voice calls are aggregated to the correct MDN call category based on Network of Call origin and B Number | MSISDN is connected to a SM eligible price plan without Business Traveller | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Network of Call Origin TWN and record type 51 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 50856 | 7701000096 | 123000096 | CG | EBUL_250MB_BT | VBF4INV |  | 1 | Yes
97 | Receiving Calls in Andorra | Confirm that roaming voice calls are aggregated to the correct MDN call category based on Network of Call origin and B Number | MSISDN is connected to a SM eligible price plan without Business Traveller | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Network of Call Origin AND and record type 51 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 50857 | 7701000097 | 123000097 | CG | BUSOPT8 | VBODV5 |  | 1 | Yes
98 | Receiving Calls in ROW2C4 | Confirm that roaming voice calls are aggregated to the correct MDN call category based on Network of Call origin and B Number | MSISDN is connected to a SM eligible price plan without Business Traveller | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Network of Call Origin ETH and record type 51 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 50858 | 7701000098 | 123000098 | CG | EBUL_250MB_BT | VBUSF12 |  | 1 | Yes
99 | Receiving Calls in ROW2C1 | Confirm that roaming voice calls are aggregated to the correct MDN call category based on Network of Call origin and B Number | MSISDN is connected to a SM eligible price plan without Business Traveller | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Network of Call Origin BTN and record type 51 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 50859 | 7701000099 | 123000099 | CG | BUSOPT8 | VBODV5 |  | 1 | Yes
100 | Receiving Calls in ROW2_Cfur | Confirm that roaming voice calls are aggregated to the correct MDN call category based on Network of Call origin and B Number | MSISDN is connected to a SM eligible price plan without Business Traveller | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Network of Call Origin UZB and record type 51 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 50860 | 7701000100 | 123000100 | CG | EBUL_250MB_BT | VBF9INV |  | 1 | Yes
101 | Receiving Calls in ROW2C3 | Confirm that roaming voice calls are aggregated to the correct MDN call category based on Network of Call origin and B Number | MSISDN is connected to a SM eligible price plan without Business Traveller | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Network of Call Origin LCA and record type 51 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 50861 | 7701000101 | 123000101 | CG | BUSOPT12 | VBODV1 |  | 1 | Yes
102 | Receiving Calls in EC_further | Confirm that roaming voice calls are aggregated to the correct MDN call category based on Network of Call origin and B Number | MSISDN is connected to a SM eligible price plan without Business Traveller | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Network of Call Origin BRA and record type 51 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 50862 | 7701000102 | 123000102 | CG | PS_2017_2GB | PSE0GB2M |  | 1 | Yes
103 | Receiving Calls in asia_pacific_Cfur | Confirm that roaming voice calls are aggregated to the correct MDN call category based on Network of Call origin and B Number | MSISDN is connected to a SM eligible price plan without Business Traveller | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Network of Call Origin NZL and record type 51 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 50863 | 7701000103 | 123000103 | CG | PS_2017_3GB | PIV3G36 |  | 1 | Yes
104 | Receiving Calls in usa_canada_Cfur | Confirm that roaming voice calls are aggregated to the correct MDN call category based on Network of Call origin and B Number | MSISDN is connected to a SM eligible price plan without Business Traveller | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Network of Call Origin CAN and record type 51 3. View the usage aggregation via the MDN web Client | The 60 second call is aggregated to MDN call category 50864 | 7701000104 | 123000104 | CG | EBUL_250MB_BT | VBF4INV |  | 1 | Yes
105 | b -number look up | Confirm that the B number lookup correctly identifies the roaming country | MSISDN is connected to a SM eligible price plan without Business Traveller | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Network of Call Origin CAN and b number starting 00387 (Bosnia) 3. Generate a 1 minute call with Network of Call Origin CAN and b number starting 00379 (Italy) 4. View the usage aggregation via the MDN web Client | The first 60 second call is aggregated to MDN call category 50465 (for bosnia) The second 60 second call is aggregated to MDN call category 50464 (for Italy) | 7701000105 | 123000105 | CG | BUSOPT8 | VBODV5 |  | 1 | Yes

## Roaming SMS
Test ID | Test Case | Test Objective | Pre condition | Test Steps | expected result | Test Data - CTN | Test Data - BAN | Test data - Source system | Test Data - Priceplan Type | Test Data - Priceplan | Test Data - SOCs | Test Data - rollover day | TIL stub | Result
106 | Roaming SMS from Europe_1_Cfree to Europe_1_Cfree | Confirm that roaming SMS are aggregated to the correct MDN call category based on Network of Call origin and B Number | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate an SMS with Network of Call Origin DEU and B number with prefix of 0042- (CZE) 3. View the usage aggregation via the MDN web Client | The SMS is aggregated to MDN call category 60024 | 7701000106 | 123000106 | CG | EBU9_RS0_DS | 1NETBPVUH |  | 1 | Yes
107 | Roaming SMS from Europe_1_Cfree to Europe_1a_Cfree | Confirm that roaming SMS are aggregated to the correct MDN call category based on Network of Call origin and B Number | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate an SMS with Network of Call Origin DEU and B number with prefix of 00262 (REU) 3. View the usage aggregation via the MDN web Client | The SMS is aggregated to MDN call category 60025 | 7701000107 | 123000107 | CG | EBU9_RS0_DS | 1NETBPVUH |  | 1 | Yes
108 | Roaming SMS from Europe_1_Cfree to Europe_2_Cfur | Confirm that roaming SMS are aggregated to the correct MDN call category based on Network of Call origin and B Number | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate an SMS with Network of Call Origin DEU and B number with prefix of 00355 (ALB) 3. View the usage aggregation via the MDN web Client | The SMS is aggregated to MDN call category 60026 | 7701000108 | 123000108 | CG | EBU_1NET_PPM_1 | 1NETPC60P |  | 1 | Yes
109 | Roaming SMS from Europe_1_Cfree to Europe_2b_Cfree | Confirm that roaming SMS are aggregated to the correct MDN call category based on Network of Call origin and B Number | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate an SMS with Network of Call Origin DEU and B number with prefix of 0090 (TUR) 3. View the usage aggregation via the MDN web Client | The SMS is aggregated to MDN call category 60027 | 7701000109 | 123000109 | CG | EBU9_RS2_DS | BUADTB02 |  | 1 | Yes
110 | Roaming SMS from Europe_1_Cfree to ROW_Cfur | Confirm that roaming SMS are aggregated to the correct MDN call category based on Network of Call origin and B Number | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate an SMS with Network of Call Origin DEU and B number with prefix of 00880 (BGD) 3. View the usage aggregation via the MDN web Client | The SMS is aggregated to MDN call category 60030 | 7701000110 | 123000110 | CG | EBU9_RS2_DS | BUADTB02 |  | 1 | Yes
111 | Roaming SMS from Europe_1_Cfree to ROW_C4 | Confirm that roaming SMS are aggregated to the correct MDN call category based on Network of Call origin and B Number | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate an SMS with Network of Call Origin DEU and B number with prefix of 00963 (Syria) 3. View the usage aggregation via the MDN web Client | The SMS is aggregated to MDN call category 60031 | 7701000111 | 123000111 | CG | PS_2017_3GB | PIV3G36 |  | 1 | Yes
112 | Roaming SMS from Europe_1_Cfree to ROW_C1 | Confirm that roaming SMS are aggregated to the correct MDN call category based on Network of Call origin and B Number | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate an SMS with Network of Call Origin DEU and B number with prefix of 00250 (Rwanda) 3. View the usage aggregation via the MDN web Client | The SMS is aggregated to MDN call category 60032 | 7701000112 | 123000112 | CG | EBUL_250MB_BT | VBF4INV |  | 1 | Yes
113 | Roaming SMS from Europe_1_Cfree to ROW_C2 | Confirm that roaming SMS are aggregated to the correct MDN call category based on Network of Call origin and B Number | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate an SMS with Network of Call Origin DEU and B number with prefix of 00263 (Zimbabwe) 3. View the usage aggregation via the MDN web Client | The SMS is aggregated to MDN call category 60033 | 7701000113 | 123000113 | CG | BUSOPT8 | VBODV5 |  | 1 | Yes
114 | Roaming SMS from Europe_1_Cfree to ROW_C3 | Confirm that roaming SMS are aggregated to the correct MDN call category based on Network of Call origin and B Number | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate an SMS with Network of Call Origin DEU and B number with prefix of 00264 (Namibia) 3. View the usage aggregation via the MDN web Client | The SMS is aggregated to MDN call category 60035 | 7701000114 | 123000114 | CG | EBUL_250MB_BT | VBUSF12 |  | 1 | Yes
115 | Roaming SMS from Europe_1_Cfree to Taiwan | Confirm that roaming SMS are aggregated to the correct MDN call category based on Network of Call origin and B Number | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate an SMS with Network of Call Origin DEU and B number with prefix of 00886 (Taiwan) 3. View the usage aggregation via the MDN web Client | The SMS is aggregated to MDN call category 60036 | 7701000115 | 123000115 | CG | EBUL_250MB_BT | VBUSF12 |  | 1 | Yes
116 | Roaming SMS from Europe_1_Cfree to Andorra | Confirm that roaming SMS are aggregated to the correct MDN call category based on Network of Call origin and B Number | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate an SMS with Network of Call Origin DEU and B number with prefix of 00376 (Andorra) 3. View the usage aggregation via the MDN web Client " | The SMS is aggregated to MDN call category 60037 | 7701000116 | 123000116 | CG | EBUL_250MB_BT | VBF9INV |  | 1 | Yes
117 | Roaming SMS from Europe_1_Cfree to ROW2C4 | Confirm that roaming SMS are aggregated to the correct MDN call category based on Network of Call origin and B Number | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate an SMS with Network of Call Origin DEU and B number with prefix of 00251 (Ethiopia) 3. View the usage aggregation via the MDN web Client | The SMS is aggregated to MDN call category 60038 | 7701000117 | 123000117 | CG | BUSOPT12 | VBODV1 |  | 1 | Yes
118 | Roaming SMS from Europe_1_Cfree to ROW2C1 | Confirm that roaming SMS are aggregated to the correct MDN call category based on Network of Call origin and B Number | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate an SMS with Network of Call Origin DEU and B number with prefix of 00975 (Bhutan) 3. View the usage aggregation via the MDN web Client | The SMS is aggregated to MDN call category 60039 | 7701000118 | 123000118 | CG | PS_2017_2GB | PSE0GB2M |  | 1 | Yes
119 | Roaming SMS from Europe_1_Cfree to ROW2_Cfur | Confirm that roaming SMS are aggregated to the correct MDN call category based on Network of Call origin and B Number | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate an SMS with Network of Call Origin DEU and B number with prefix of 00998 (Uzbekistan) 3. View the usage aggregation via the MDN web Client | The SMS is aggregated to MDN call category 60040 | 7701000119 | 123000119 | CG | PS_2017_2GB | PSE0GB2M |  | 1 | Yes
120 | Roaming SMS from Europe_1_Cfree to ROW2C3 | Confirm that roaming SMS are aggregated to the correct MDN call category based on Network of Call origin and B Number | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate an SMS with Network of Call Origin DEU and B number with prefix of 001758 (St Lucia) 3. View the usage aggregation via the MDN web Client " | The SMS is aggregated to MDN call category 60041 | 7701000120 | 123000120 | CG | EBU9_RS0_DS | 1NETBPVUH |  | 1 | Yes
121 | Roaming SMS from Europe_1_Cfree to EC_further | Confirm that roaming SMS are aggregated to the correct MDN call category based on Network of Call origin and B Number | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate an SMS with Network of Call Origin DEU and B number with prefix of 0057 (Columbia) 3. View the usage aggregation via the MDN web Client | The SMS is aggregated to MDN call category 60042 | 7701000121 | 123000121 | CG | EBU_1NET_PPM_1 | 1NETPC60P |  | 1 | Yes
122 | Roaming SMS from Europe_1_Cfree to aisa_pacific_Cfur | Confirm that roaming SMS are aggregated to the correct MDN call category based on Network of Call origin and B Number | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate an SMS with Network of Call Origin DEU and B number with prefix of 0064 (New Zealand) 3. View the usage aggregation via the MDN web Client | The SMS is aggregated to MDN call category 60043 | 7701000122 | 123000122 | CG | EBU9_RS2_DS | BUADTB02 |  | 1 | Yes
123 | Roaming SMS from Europe_1_Cfree to usa_canada_Cfur | Confirm that roaming SMS are aggregated to the correct MDN call category based on Network of Call origin and B Number | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate an SMS with Network of Call Origin DEU and B number with prefix of 001403 (Canada) 3. View the usage aggregation via the MDN web Client | The SMS is aggregated to MDN call category 60044 | 7701000123 | 123000123 | CG | EBU9_RS2_DS | BUADTB02 |  | 1 | Yes

## Bundle aggregation
Test ID | Test Case | Test Objective | Pre condition | Test Steps | expected result | Test Data - CTN | Test Data - BAN | Test data - Source system | Test Data - Priceplan Type | Test Data - Priceplan | Test Data - SOCs | Test Data - rollover day | TIL stub | Result
124 | Voice call are aggregated to a bundle | Confirm bundle aggregations | MSISDN is connected to a SM eligible price plan and has a voice bundle | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Tariff Class of 501 using record type 32 3. View the usage aggregation via the MDN web Client | 60 seconds are aggregated to the bundle DOMMIN50 not to the call category | 7701000124 | 123000124 | CG | PS_2017_3GB | PIV3G36 | FV50ONCE | 1 | Yes
125 | Multiple voice calls aggregated to a bundle | Confirm bundle aggregations | MSISDN is connected to a SM eligible price plan and has a voice bundle | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Tariff Class of 501 3. Generate a 40 second call with Tariff Class of 502 4. View the usage aggregation via the MDN web Client | 100 seconds are aggregated to the bundle DOMMIN50 not to the call category | 7701000125 | 123000125 | CG | EBUL_250MB_BT | VBF4INV | FV50ONCE | 1 | Yes
126 | Fully consumed vocie bundle | Confirm bundle aggregations | MSISDN is connected to a SM eligible price plan and has a voice bundle | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate 3000 seconds of calls with Tariff Class of 501 using record type 32 3. View the usage aggregation via the MDN web Client | The voice bundle DOMMIN50 is fully consumed | 7701000126 | 123000126 | CG | BUSOPT8 | VBODV5 | FV50ONCE | 1 | Yes
127 | Aggregating to voice Call Category when bundle is consumed | Confirm bundle aggregations | MSISDN is connected to a SM eligible price plan and has a voice bundle that has been consumed | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Tariff Class of 501 using record type 32 3. View the usage aggregation via the MDN web Client | The call is aggregated to the call category 10006 not the bundle | 7701000127 | 123000127 | CG | EBUL_250MB_BT | VBUSF12 | FV50ONCE | 1 | Yes
128 | Voice bundle re-set to zero on month rollover | Confirm bundle aggregations | MSISDN is connected to a SM eligible price plan and has a voice bundle | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Tariff Class of 501 3. Generate a 40 second call with Tariff Class of 502 4. View the usage aggregation via the MDN web Client | The bundle aggregation is 100 seconds on the last day of the bill month and zero on the first day of the next bill month | 7701000128 | 123000128 | CG | EBUL_250MB_BT | VBUSF12 | FV50ONCE | 1 | Yes
129 | SMS are aggregated to a bundle | Confirm bundle aggregations | MSISDN is connected to a SM eligible price plan and has an SMS bundle | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate an MO SMS with GSM Service 177500 3. View the usage aggregation via the MDN web Client | 1 SMS is aggregated to the bundle DOMSMS10 not to the call category | 7701000129 | 123000129 | CG | EBUL_250MB_BT | VBF9INV | 10SMSBUN | 1 | Yes
130 | Multiple SMS aggregated to a bundle | Confirm bundle aggregations | MSISDN is connected to a SM eligible price plan and has an SMS bundle | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate 5 MO SMS with GSM Service 177500 3. View the usage aggregation via the MDN web Client | 5 SMS are aggregated to the bundle DOMSMS10 not to the call category | 7701000130 | 123000130 | CG | BUSOPT12 | VBODV1 | 10SMSBUN | 1 | Yes
131 | Fully consumed SMS bundle | Confirm bundle aggregations | MSISDN is connected to a SM eligible price plan and has an SMS bundle | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate 10 MO SMS with GSM Service 177500 3. View the usage aggregation via the MDN web Client | The SMS bundle DOMSMS10 is fully consumed | 7701000131 | 123000131 | CG | PS_2017_2GB | PSE0GB2M | 10SMSBUN | 1 | Yes
132 | Aggregating to SMS Call Category when bundle is consumed | Confirm bundle aggregations | MSISDN is connected to a SM eligible price plan and has a SMS bundle that has been consumed | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate an MO SMS with GSM Service 177500 3. View the usage aggregation via the MDN web Client | The SMS is aggregated to MDN call category 30028 | 7701000132 | 123000132 | CG | PS_2017_2GB | PSE0GB2M | 10SMSBUN | 1 | Yes
133 | SMS bundle re-set to zero on month rollover | Confirm bundle aggregations | MSISDN is connected to a SM eligible price plan and has an SMS bundle | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate 5 MO SMS with GSM Service 177500 3. View the usage aggregation via the MDN web Client | The bundle aggregation is 5 SMS on the last day of the bill month and zero on the first day of the next bill month | 7701000133 | 123000133 | CG | EBU9_RS0_DS | 1NETBPVUH | 10SMSBUN | 1 | Yes

## Traveller aggregation
Test ID | Test Case | Test Objective | Pre condition | Test Steps | expected result | Test Data - CTN | Test Data - BAN | Test data - Source system | Test Data - Priceplan Type | Test Data - Priceplan | Test Data - SOCs | Test Data - rollover day | TIL stub | Result
134 | roaming calls in Europe to a Europe destination | Confirm that calls are aggregated as domstic calls | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Network of Call Origin DEU and B number with prefix or 0042- (CZE) 3. View the usage aggregation via the MDN web Client | Call are aggregated as domestic call category 10007 | 7701000134 | 123000134 | CG | PS_2017_3GB | PIV3G36 |  | 1 | yes
135 | roaming calls in Europe to a non Europe destination | Confirm that calls are aggregated as roaming calls | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Network of Call Origin DEU and B number with prefix or 00963 (Syria) 3. View the usage aggregation via the MDN web Client | Call are aggregated as normal roaming calls | 7701000135 | 123000135 | CG | EBUL_250MB_BT | VBF4INV |  | 1 | yes
136 | roaming calls in Europe back to the UK | Confirm that calls are aggregated as domstic calls | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Network of Call Origin DEU and B number with prefix or 0044 (UK) 3. View the usage aggregation via the MDN web Client " | Call are aggregated as domestic call category 10007 | 7701000136 | 123000136 | CG | BUSOPT8 | VBODV5 |  | 1 | yes
137 | roaming calls in Europe 2 to a ROW destination | Confirm that calls are aggregated as domstic or international calls | MSISDN is connected to a SM eligible price plan and has Business Traveller | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Network of Call Origin TUR and B number with prefix or 0057 (Columbia) 3. View the usage aggregation via the MDN web Client | Calls are aggregated as international calls category 4008 | 7701000137 | 123000137 | CG | EBUL_250MB_BT | VBUSF12 | BUSTRA001 | 1 | yes
138 | roaming calls in ROW(BT zone) in country | Confirm that calls are aggregated as domstic or international calls | MSISDN is connected to a SM eligible price plan and has Business Traveller | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Network of Call Origin JPN and B number with prefix or 0081 (Japan) 3. View the usage aggregation via the MDN web Client | Call are aggregated as domestic call category 10007 | 7701000138 | 123000138 | CG | EBUL_250MB_BT | VBUSF12 | BUSTRA001 | 1 | yes
139 | roaming calls in ROW(BT zone) to Europe | Confirm that calls are aggregated as domstic or international calls | MSISDN is connected to a SM eligible price plan and has Business Traveller | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Network of Call Origin JPN and B number with prefix or 0049 (Germany) using record type 50 3. View the usage aggregation via the MDN web Client | Call are aggregated as standard roaming calls | 7701000139 | 123000139 | CG | EBUL_250MB_BT | VBUSF12 | BUSTRA001 | 1 | yes
140 | roaming SMS in Europe 2 to a ROW destination | Confirm that calls are aggregated as domstic or international calls | MSISDN is connected to a SM eligible price plan and has Business Traveller | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate an SMS with Network of Call Origin TUR and B number with prefix or 00264 (Namibia) 3. View the usage aggregation via the MDN web Client | SMS are aggregated as international call category 30023 | 7701000140 | 123000140 | CG | BUSOPT12 | VBODV1 | BUSTRA001 | 1 | yes
141 | roaming SMS in Europe back to the UK | Confirm that calls are aggregated as domstic or international calls | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate an SMS with Network of Call Origin DEU and B number with prefix or 0044 (UK) 3. View the usage aggregation via the MDN web Client | SMS are aggregated as domestic call category 30028 | 7701000141 | 123000141 | CG | PS_2017_2GB | PSE0GB2M |  | 1 | yes

## Web Client
Test ID | Test Case | Test Objective | Pre condition | Test Steps | expected result | Test Data - CTN | Test Data - BAN | Test data - Source system | Test Data - Priceplan Type | Test Data - Priceplan | Test Data - SOCs | Test Data - rollover day | TIL stub | Result
142 | View UK voice aggregations by Call Category | Confirm the information is viewable | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Tariff Class of 501 using record type 32 3. View the usage aggregation via the MDN web Client | The call is aggregated with MDN call category 10006 is visble via the web client | 7701000142 | 123000142 | CG | EBU9_RS0_DS | 1NETBPVUH |  | 1 | Yes
143 | View UK SMS aggregations by Call Category | Confirm the information is viewable | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate an MO SMS with GSM Service 600790 3. View the usage aggregation via the MDN web Client | The SMS is aggregated with MDN call category 30035 is visible via the web client | 7701000143 | 123000143 | CG | EBU9_RS0_DS | 1NETBPVUH |  | 1 | Yes
144 | View UK MMS aggregations by Call Category | Confirm the information is viewable | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate an MMS CDR with Tariff Class 4005 and Network of Call Origin GBR 3. View the usage aggregation via the MDN web Client | The MMS is aggregated with MDN call category 20021 is visible via the web client | 7701000144 | 123000144 | CG | EBU_1NET_PPM_1 | 1NETPC60P |  | 1 | Yes
145 | View International voice aggregations by Call Category | Confirm the information is viewable | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Tariff Class of 687 and B number with prefix or 00886 (Taiwan) 3. View the usage aggregation via the MDN web Client | The call is aggregated with MDN call category 40021 is visible via the web client | 7701000145 | 123000145 | CG | EBU9_RS2_DS | BUADTB02 |  | 1 | Yes
146 | View roaming voice aggregations by Call Category | Confirm the information is viewable | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate a 1 minute call with Network of Call Origin DEU and B number with prefix or 0057 (Columbia) 3. View the usage aggregation via the MDN web Client | The call is aggregated with MDN call category 50044 is visible via the web client | 7701000146 | 123000146 | CG | EBU9_RS2_DS | BUADTB02 |  | 1 | Yes
147 | View roaming SMS aggregations by Call Category | Confirm the information is viewable | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate an SMS with Network of Call Origin DEU and B number with prefix or 0090 (TUR) 3. View the usage aggregation via the MDN web Client | The SMS is aggregated with MDN call category 60027 is visible via the web client | 7701000147 | 123000147 | CG | PS_2017_3GB | PIV3G36 |  | 1 | Yes
148 | View roaming MMS aggregations by Call Category | Confirm the information is viewable | MSISDN is connected to a SM eligible price plan | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate an MMS CDR with Tariff Class 4015 and Network of Call Origin AUD VF 3. View the usage aggregation via the MDN web Client | The MMS is aggregated with MDN call category 20065 is visible via the web client | 7701000148 | 123000148 | CG | PS_2017_3GB | PIV3G36 |  | 1 | Yes

## TAR GUI
Test ID | Test Case | Test Objective | Pre condition | Test Steps | expected result | Test Data - CTN | Test Data - BAN | Test data - Source system | Test Data - Priceplan Type | Test Data - Priceplan | Test Data - SOCs | Test Data - rollover day | TIL stub | Result
155 | Charging field in Priceplan Notification | Confirm TAR GUI behaviour | none | 1. Select an exising Priceplan Type 2. Set the new Charging field to Y 3. Save the update |  | not applicable
156 | Charging field in SOC Notification | Confirm TAR GUI behaviour | none | 1. Select an exising Priceplan Type 2. Set the new Charging field to Y 3. Save the update |  | not applicable
157 | Create SM priceplan | Confirm TAR GUI behaviour | none | 1. From the Priceplan Type screen create a new SM Priceplan type 2. Save the changes |  | not applicable
158 | Add SM priceplan type to an existing Priceplan Type | Confirm TAR GUI behaviour | none | 1. From the Priceplan Type screen select a price plan and add an SM priceplan type 2. Save the changes |  | not applicable
159 | Create rating for an SM Priceplan type | Confirm TAR GUI behaviour | none | 1. From the New rating screen select an SM Priceplan Type 2. Enter the rates for each call category 3. Save the changes |  | not applicable
160 | Amend rating for an SM price plan type | Confirm TAR GUI behaviour | none | 1. From the New rating screen select an SM Priceplan Type 2. Amend the rates for each call category 3. Save the changes |  | not applicable
161 | Create rating for a new SM priceplan type using an existing template | Confirm TAR GUI behaviour | none | 1. From the New rating screen select an SM Priceplan Type 2. Copy and re-name to create a rating for a new SM priceplan type 3. Save the changes |  | not applicable
162 | Create a new SM bundle and thresholds | Confirm TAR GUI behaviour | none | 1. From the New SM Bundle screen enter a new bundle 2. Add thresholds to the bunde 3. Save the changes |  | not applicable
163 | Map an SM bundle to a SOC or SM priceplan type | Confirm TAR GUI behaviour | none | 1. From the New SM Bundle screen select a bndle 2. Map to a SOC code 3. Save the changes |  | not applicable
164 | Map Call categories to an SM bundle | Confirm TAR GUI behaviour | none | 1. From the New SM Bundle screen select a bndle 2. Map to multiple call categories 3. Save the changes |  | not applicable

## Regression
Test ID | Test Case | Test Objective | Pre condition | Test Steps | expected result | Test Data - CTN | Test Data - BAN | Test data - Source system | Test Data - Priceplan Type | Test Data - Priceplan | Test Data - SOCs | Test Data - rollover day | TIL stub | Result
149 | Consumer rating for 50 euro cap | Regression of existing data rating | Consumer is opted into data capping | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate 2GB domestic OOB data usage while in France 3. View the results via the MDN web Client | 50 euro cap is triggered | 7701000149 | 123000149 | LG | CBU13_5GB | 1O5O5GLZ |  | 1 | yes
150 | Enterprise rating for 50 euro cap | Regression of existing data rating | Enerprise priceplan and opted into data capping | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate 8MB data usage while in Tunisia 3. View the results via the MDN web Client | 50 euro cap is triggered | 7701000150 | 123000150 | LG | EBUL_250MB_BT | VBF4INV |  | 1 | yes
151 | Data sharer OOB rating | Regression of existing data rating | Customer is a data sharer leader | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate 1GB OOB data sharer usage for the group 3. View the usage aggregation via the MDN web Client | 1GB OOB charge of £12.77 | 7701000151 | 123000151 | CG | EBUL_250MB_BT | VBUSF05 | DSBUSC,CAP_1GB | 1 | yes
[6 empty] | 7701100151 | 123000151 | CG | EBUL_250MB_BT | VBUSF05 | RS_5GB,DSBUSP | 1 | yes
152 | Standard notifications | Regression of existing data roaming notiications | none | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate 8MB data usage while in Tunisia 3. View the results via the MDN web Client | The customer recieves data roaming notfications | 7701100152 | 123000152 | LG | CBU13_5GB | 1O5O5GLZ |  | 1 | yes
153 | Actioning notifications | Regression of exisitng actioning rules | none | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate 2GB domestic OOB domestic data 3. View the results via the MDN web Client | The customer is notified of their OOB data usage | 7701100153 | 123000153 | LG | CBU13_5GB | 1O5O5GLZ |  | 1 | yes
154 | Email notifications | Regression of existing email notificaitons | customer is opted into email notificatons | 1. Load subscriber via the subscriber file and view in the Web Client Subscriber Query 2. Generate 8MB data usage while in Tunisia 3. View the results via the MDN web Client | The customer recieives emai notificaitons | 7701100154 | 123000154 | LG | CBU13_5GB | 1O5O5GLZ | EMAIL_PER | 1 | yes

## Test subs file
Test Data - CTN | Test Data - BAN | Source System | Test Data - Priceplan Type | Test Priceplan | Test Data - SOCs | Test Data - rollover day | GetSubscriber - bars | GetExistingPriceplan stub ? | spid
7023000001 | 123000001 | CG | BUSOPT1 | VBODV13 | CAP4GB | 1 | yes | yes
7023000002 | 123000001 | CG | BUSOPT2 | VBODV12 | CAP4GB | 1 | yes | yes
7023000003 | 123000001 | CG | BUSOPT3 | VBOVDV28 | CAP4GB,EXT1GB | 1 | yes | yes
7023000004 | 123000001 | CG | BUSOPT4 | VBODV9 | CAP6GB | 1 | yes | yes
7023000005 | 123000001 | CG | BUSOPT5 | VBOVDV21 | CAP2GB | 1 | yes | yes
7023000006 | 123000001 | CG | BUSOPT6 | VBOVDV18 | CAP2GB | 1 | yes | yes
7023000007 | 123000002 | CG | EBUL_250MB_BT | VBUSF05 | CAP2GB,BUSTRA002,DSBUSC | 1 | yes | yes
7023100007 | 123000002 | CG | EBUL_250MB_BT | VBUSF05 | RS_5GB,DSBUSP,CAP6GB | 1 | yes | yes
7023000008 | 123000003 | CG | EBUL_250MB_BT | VBUSF05 | CAP2GB,BUSTRA002,DSBUSC | 1 | yes | yes
7023100008 | 123000003 | CG | EBUL_250MB_BT | VBUSF05 | RS_5GB,DSBUSP,CAP6GB | 1 | yes | yes
7023000009 | 123000001 | CG | BUSOPT7 | VBODV6 | CAP8GB,COMBOPASS | 1 | yes | yes
7023000010 | 123000001 | CG | CBU14_2GB_MBB | MBB12GL | CAPOFF | 1 | yes | yes
7023000011 | 123000001 | LG | BUSOPT1 | VBODV13 | CAP4GB | 1 | yes | yes
7023000012 | 123000001 | LG | BUSOPT1 | VBODV13 | CAP4GB | 1 | yes | yes
7023000013 | 123000001 | LG | BUSOPT1 | VBODV13 | CAP4GB | 1 | yes | yes
7023000014 | 123000001 | LG | BUSOPT1 | VBODV13 | CAP4GB | 1 | yes | yes
7023000015 | 123000001 | LG | BUSOPT1 | VBODV13 | CAP4GB | 1 | yes | yes
7023000016 | 123000001 | LG | BUSOPT1 | VBODV13 | CAP4GB | 1 | yes | yes
7023000017 | 123000001 | LG | BUSOPT1 | VBODV13 |  | 1 | yes | yes
7023000018 | 123000001 | LG | BUSOPT12 | VBODV1 |  | 1 | yes | yes
7023000019 | 123000001 | LG | BUSOPT13 | VBODV10 |  | 1 | yes | yes
7023000020 | 123000001 | LG | BUSOPT8 | VBODV5 |  | 1 | yes | yes
7023000021 | 123000001 | LG | BUSOPT9 | VBOVDV9 |  | 1 | yes | yes
7023000022 | 123000001 | LG | BUSOPT7 | VBOVDV15,BOPROAM1 |  | 1 | yes | yes
7023000023 | 123000001 | LG | BUSOPT12 | VBOVDV1 |  | 1 | yes | yes
7023000024 | 123000001 | LG | BUSOPT8 | VBOVDV12 |  | 1 | yes | yes
7023000025 | 123000001 | LG | BUSOPT4 | VBOVDV24 |  | 1 | yes | yes
7023000026 | 123000001 | LG | BUSOPT3 | VBODV11 |  | 1 | yes | yes
7023000027 | 123000001 | LG | BUSOPT2 | VBODV12 |  | 1 | yes | yes
7023000028 | 123000001 | CG | BUSOPT6 | VBOVDV17 | BUSOPTDT | 1 | yes | yes
7023000029 | 123000001 | CG | BUSOPT6 | VBOVDV17 | BUSOPTDT,BOPROAM1 | 1 | yes | yes
7023000030 | 123000001 | CG | BUSOPT6 | VBOVDV17 | BUSOPTDT | 1 | yes | yes
7023000031 | 123000001 | CG | BUSOPT6 | VBOVDV17 | BUSOPTDT,1GBRBOP | 1 | yes | yes
7023000032 | 123000001 | CG | BUSOPT6 | VBOVDV17 | 1GBRBOP | 1 | yes | yes
7023000033 | 123000001 | CG | BUSOPT6 | VBOVDV17 | BOPROAM1,BUSCAP200 | 1 | yes | yes
7023100028 | 123000001 | CG | BUSOPT6 | VBOVDV17 | BUSOPTDT | 1 | yes | yes
7023100029 | 123000001 | CG | BUSOPT6 | VBOVDV17 | BUSOPTDT,BOPROAM1 | 1 | yes | yes
7023100030 | 123000001 | CG | BUSOPT6 | VBOVDV17 | BUSOPTDT | 1 | yes | yes
7023100031 | 123000001 | CG | BUSOPT6 | VBOVDV17 | BUSOPTDT,1GBRBOP | 1 | yes | yes
7023100032 | 123000001 | CG | BUSOPT6 | VBOVDV17 | 1GBRBOP,BOPROAM1 | 1 | yes | yes
7023100033 | 123000001 | CG | BUSOPT6 | VBOVDV17 | BOPROAM1,BUSCAP200 | 1 | yes | yes
7023100022 | 123000001 | LG | BUSOPT7 | VBOVDV15,BOPROAM1 |  | 1 | yes | yes
7023100009 | 123000001 | CG | BUSOPT7 | VBODV6 | CAP8GB,COMBOPASS | 1 | yes | yes
7023100012 | 123000001 | LG | BUSOPT1 | VBODV13 | CAP4GB | 1 | yes | yes
7023100013 | 123000001 | LG | BUSOPT1 | VBODV13 | CAP4GB | 1 | yes | yes

## document control
MDN - Spend Manager drop 1
Revision History
Version | Date | Author | Change Summary
0.1 |  |  | First draft
Distribution List
Name | Position | Email