## Introduction
Zero Rating Test Plan
Author
Firasat Shukla
Document Version
0.1
Introduction
This Test plan identifies: 1. Test Cases identified for the zero rate functionality implemented for VBC.
Contents - Areas of Testing
In Scope - System testing for Zero Rating Capping Functionality This testing for the 2 New PITs “**Capping charges above a threshold” and “**Total charge accumulation”
Out Of scope - MDN related actions impacting capping/override.
References
Gemini PC MDN Usage Capping High Level Design v1.0.docx Minispecs_VBC_9151n9152_v0.2.doc

## PIT Import and RTS
Test ID | Test Case | Test Objective | Path | Test Step | expected result | CRID | Responsible_App | Test_Level | Topic_Id | Version | Status | Story_Name | Detected_In_App | Involved_App | Test_Step_No
1 | TC_1_Import new PITs to PAT PC | Test Objective: To import 2 New PITs “**Capping charges above a threshold” and “**Total charge accumulation” to PC Pre Condition: Dev and UT of new PITs completed | VFUK-Mobile\VBC\MDN_Drop1\PIT_Import_and_RTS | Import new PITs to PAT PC | Import of PIT is completed successfully | VBC | MDN | 07-System Test | CMD | Drop1 | Design | Event Processing | MDN | MDN | Step 1
2 | TC_2_Finalize the new PITs | Test Objective: To Validate Finalization Pre Condition: PITs imported | VFUK-Mobile\VBC\MDN_Drop1\PIT_Import_and_RTS | Finalize the new PITs | Finalization completed successfully | VBC | MDN | 07-System Test | CMD | Drop1 | Design | Event Processing | MDN | MDN | Step 1
2 | TC_2_Perform Business Implementation of the new PITS | Test Objective: Business Implementation as per the Test Scripts Pre Condition: Finalized PITs available in Product Catalog | VFUK-Mobile\VBC\MDN_Drop1\PIT_Import_and_RTS | Perform Business Implementation of the new PITS | Business Imp completed. | VBC | MDN | 07-System Test | CMD | Drop1 | Design | Event Processing | MDN | MDN | Step 1
3 | TC_3_Finalize the new BI | Test Objective: To Validate Finalization Pre Condition: BI correction available | VFUK-Mobile\VBC\MDN_Drop1\PIT_Import_and_RTS | Finalize the new BI | Finalization completed successfully | VBC | MDN | 07-System Test | CMD | Drop1 | Design | Event Processing | MDN | MDN | Step 1
4 | TC_4_Release | Test Objective: To Validate Release Pre Condition: New PIT/BI Finalized corrections available | VFUK-Mobile\VBC\MDN_Drop1\PIT_Import_and_RTS | Validate Release | Release completed successfully | VBC | MDN | 07-System Test | CMD | Drop1 | Design | Event Processing | MDN | MDN | Step 1
5 | TC_5_Distribute | Test Objective: To Validate Distribution Pre Condition: Release Correction available | VFUK-Mobile\VBC\MDN_Drop1\PIT_Import_and_RTS | Validate Distribution | Distribute completed successfully | VBC | MDN | 07-System Test | CMD | Drop1 | Design | Event Processing | MDN | MDN | Step 1

## Apply £20Capping
Test ID | Test Case | Test Objective | Path | Test Steps | expected result | CRID | Responsible_App | Test_Level | Topic_Id | Version | Status | Story_Name | Detected_In_App | Involved_App | Test_Step_No
7 | TC_7_Domestic MO calls | Test Objective: To validate the rating/capping functionality for domestic voice calls Pre Condition: Apply £20 Capping offer | VFUK-Mobile\VBC\MDN_Drop1\Apply_£20Capping | Rate event with predefined SF/Tariff | Calls to be rated as expected and capped at £20 and all calls after the capped amount to be rated a zero charge | VBC | MDN | 07-System Test | CMD | Drop1 | Design | Event Processing | MDN | MDN | Step 1
8 | TC_8_Domestic MO SMS | Test Objective: To validate the ratring/capping functionality for domestic SMS events Pre Condition: Apply £20 Capping offer | VFUK-Mobile\VBC\MDN_Drop1\Apply_£20Capping | Rate event with predefined SF/Tariff | Calls to be rated as expected and capped at £20 and all calls after the capped amount to be rated a zero charge | VBC | MDN | 07-System Test | CMD | Drop1 | Design | Event Processing | MDN | MDN | Step 1
9 | TC_9_Domestic MMS picture | Test Objective: To validate the rating/capping functionality for MMS PT Pre Condition: Apply £20 Capping offer | VFUK-Mobile\VBC\MDN_Drop1\Apply_£20Capping | Rate event with predefined SF/Tariff | Calls to be rated as expected and capped at £20 and all calls after the capped amount to be rated a zero charge | VBC | MDN | 07-System Test | CMD | Drop1 | Design | Event Processing | MDN | MDN | Step 1
10 | TC_10_International call to Europe | Test Objective: To validate the ratring/capping functionality for International Calls Pre Condition: Apply £20 Capping offer | VFUK-Mobile\VBC\MDN_Drop1\Apply_£20Capping | Rate event with predefined SF/Tariff | Calls to be rated as expected and capped at £20 and all calls after the capped amount to be rated a zero charge | VBC | MDN | 07-System Test | CMD | Drop1 | Design | Event Processing | MDN | MDN | Step 1
11 | TC_11_International call to US | Test Objective: To validate the ratring/capping functionality for International Calls Pre Condition: Apply £20 Capping offer | VFUK-Mobile\VBC\MDN_Drop1\Apply_£20Capping | Rate event with predefined SF/Tariff | Calls to be rated as expected and capped at £20 and all calls after the capped amount to be rated a zero charge | VBC | MDN | 07-System Test | CMD | Drop1 | Design | Event Processing | MDN | MDN | Step 1
12 | TC_12_International SMS to Europe | Test Objective: To validate the ratring/capping functionality for International SMS Pre Condition: Apply £20 Capping offer | VFUK-Mobile\VBC\MDN_Drop1\Apply_£20Capping | Rate event with predefined SF/Tariff | Calls to be rated as expected and capped at £20 and all calls after the capped amount to be rated a zero charge | VBC | MDN | 07-System Test | CMD | Drop1 | Design | Event Processing | MDN | MDN | Step 1
13 | TC_13_International SMS to US | Test Objective: To validate the ratring/capping functionality for International SMS Pre Condition: Apply £20 Capping offer | VFUK-Mobile\VBC\MDN_Drop1\Apply_£20Capping | Rate event with predefined SF/Tariff | Calls to be rated as expected and capped at £20 and all calls after the capped amount to be rated a zero charge | VBC | MDN | 07-System Test | CMD | Drop1 | Design | Event Processing | MDN | MDN | Step 1
14 | TC_14_Roaming call from Europe to Canada | Test Objective: To validate the ratring/capping functionality for roaming voice calls Pre Condition: Apply £20 Capping offer | VFUK-Mobile\VBC\MDN_Drop1\Apply_£20Capping | Rate event with predefined SF/Tariff | Calls to be rated as expected and capped at £20 and all calls after the capped amount to be rated a zero charge | VBC | MDN | 07-System Test | CMD | Drop1 | Design | Event Processing | MDN | MDN | Step 1
15 | TC_15_Roaming call from Australia - In/out country (Out to Include WT DC) | Test Objective: To validate the rating/capping functionality for roaming voice calls Pre Condition: Apply £20 Capping offer | VFUK-Mobile\VBC\MDN_Drop1\Apply_£20Capping | Rate event with predefined SF/Tariff | Calls to be rated as expected and capped at £20 and all calls after the capped amount to be rated a zero charge | VBC | MDN | 07-System Test | CMD | Drop1 | Design | Event Processing | MDN | MDN | Step 1
16 | TC_16_Roaming call from china to UK | Test Objective: To validate the ratring/capping functionality for roaming voice calls Pre Condition: Apply £20 Capping offer | VFUK-Mobile\VBC\MDN_Drop1\Apply_£20Capping | Rate event with predefined SF/Tariff | Calls to be rated as expected and capped at £20 and all calls after the capped amount to be rated a zero charge | VBC | MDN | 07-System Test | CMD | Drop1 | Design | Event Processing | MDN | MDN | Step 1
17 | TC_17_Roaming SMS in Canada | Test Objective: To validate the rating/capping functionality for roaming SMS Pre Condition: Apply £20 Capping offer | VFUK-Mobile\VBC\MDN_Drop1\Apply_£20Capping | Rate event with predefined SF/Tariff | Calls to be rated as expected and capped at £20 and all calls after the capped amount to be rated a zero charge | VBC | MDN | 07-System Test | CMD | Drop1 | Design | Event Processing | MDN | MDN | Step 1
18 | TC_18_Roaming Voice MT Calls | Test Objective: To validate the ratring/capping functionality for roaming MT calls Pre Condition: Apply £20 Capping offer | VFUK-Mobile\VBC\MDN_Drop1\Apply_£20Capping | Rate event with predefined SF/Tariff | Calls to be rated as expected and capped at £20 and all calls after the capped amount to be rated a zero charge | VBC | MDN | 07-System Test | CMD | Drop1 | Design | Event Processing | MDN | MDN | Step 1
19 | TC_19_NGN Calls | Test Objective: To validate the rating/capping functionality for NGN calls Pre Condition: Apply £20 Capping offer | VFUK-Mobile\VBC\MDN_Drop1\Apply_£20Capping | Rate event with predefined SF/Tariff | Calls to be rated as expected and capped at £20 and all calls after the capped amount to be rated a zero charge | VBC | MDN | 07-System Test | CMD | Drop1 | Design | Event Processing | MDN | MDN | Step 1
20 | TC_20_unitization 60/60 | Test Objective: To validate the ratring/capping functionality for a voice call with 60/60 unitisation Pre Condition: Apply £20 Capping offer | VFUK-Mobile\VBC\MDN_Drop1\Apply_£20Capping | Rate event with predefined SF/Tariff | Calls to be rated as expected and capped at £20 and all calls after the capped amount to be rated a zero charge | VBC | MDN | 07-System Test | CMD | Drop1 | Design | Event Processing | MDN | MDN | Step 1
21 | TC_21_unitization 60/1 | Test Objective: To validate the ratring/capping functionality for a voice call with 60/01 unitisation Pre Condition: Apply £20 Capping offer | VFUK-Mobile\VBC\MDN_Drop1\Apply_£20Capping | Rate event with predefined SF/Tariff | Calls to be rated as expected and capped at £20 and all calls after the capped amount to be rated a zero charge | VBC | MDN | 07-System Test | CMD | Drop1 | Design | Event Processing | MDN | MDN | Step 1
22 | TC_22_GPRS Domestic | Test Objective: To validate the ratring/capping functionality for domestic data calls Pre Condition: Apply £20 Capping offer | VFUK-Mobile\VBC\MDN_Drop1\Apply_£20Capping | Rate event with predefined SF/Tariff | Calls to be rated as expected and capped at £20 and all calls after the capped amount to be rated a zero charge | VBC | MDN | 07-System Test | CMD | Drop1 | Design | Event Processing | MDN | MDN | Step 1
23 | TC_23_GPRS ROAM | Test Objective: To validate the ratring/capping functionality for data roamig calls Pre Condition: Apply £20 Capping offer | VFUK-Mobile\VBC\MDN_Drop1\Apply_£20Capping | Rate event with predefined SF/Tariff | Calls to be rated as expected and capped at £20 and all calls after the capped amount to be rated a zero charge | VBC | MDN | 07-System Test | CMD | Drop1 | Design | Event Processing | MDN | MDN | Step 1
62 | TC_62_MPAY Calls | Test Objective: To validate the ratring/capping functionality for MPAY Calls Pre Condition: Apply £20 Capping offer | VFUK-Mobile\VBC\MDN_Drop1\Apply_£20Capping | Rate event with predefined SF/Tariff | Calls to be rated as expected and NOT capped at £20 . (MPAY calls OOS of VBC) | VBC | MDN | 07-System Test | CMD | Drop1 | Design | Event Processing | MDN | MDN | Step 1

## Apply £50Capping
Test ID | Test Case | Test Objective | Path | Test Steps | expected result | CRID | Responsible_App | Test_Level | Topic_Id | Version | Status | Story_Name | Detected_In_App | Involved_App | Test_Step_No
24 | TC_24_Domestic MO calls | Test Objective: To validate the rating/capping functionality for domestic voice calls Pre Condition: Apply £50 Capping offer | VFUK-Mobile\VBC\MDN_Drop1\Apply_£50Capping | Rate event with predefined SF/Tariff | Calls to be rated as expected and capped at £50 and all calls after the capped amount to be rated a zero charge | VBC | MDN | 07-System Test | CMD | Drop1 | Design | Event Processing | MDN | MDN | Step 1
25 | TC_25_Domestic MO SMS | Test Objective: To validate the ratring/capping functionality for domestic SMS events Pre Condition: Apply £50 Capping offer | VFUK-Mobile\VBC\MDN_Drop1\Apply_£50Capping | Rate event with predefined SF/Tariff | Calls to be rated as expected and capped at £50 and all calls after the capped amount to be rated a zero charge | VBC | MDN | 07-System Test | CMD | Drop1 | Design | Event Processing | MDN | MDN | Step 1
26 | TC_26_Domestic MMS picture | Test Objective: To validate the rating/capping functionality for MMS PT Pre Condition: Apply £50 Capping offer | VFUK-Mobile\VBC\MDN_Drop1\Apply_£50Capping | Rate event with predefined SF/Tariff | Calls to be rated as expected and capped at £50 and all calls after the capped amount to be rated a zero charge | VBC | MDN | 07-System Test | CMD | Drop1 | Design | Event Processing | MDN | MDN | Step 1
27 | TC_27_International call to Europe | Test Objective: To validate the ratring/capping functionality for International Calls Pre Condition: Apply £50 Capping offer | VFUK-Mobile\VBC\MDN_Drop1\Apply_£50Capping | Rate event with predefined SF/Tariff | Calls to be rated as expected and capped at £50 and all calls after the capped amount to be rated a zero charge | VBC | MDN | 07-System Test | CMD | Drop1 | Design | Event Processing | MDN | MDN | Step 1
28 | TC_28_International call to US | Test Objective: To validate the ratring/capping functionality for International Calls Pre Condition: Apply £50 Capping offer | VFUK-Mobile\VBC\MDN_Drop1\Apply_£50Capping | Rate event with predefined SF/Tariff | Calls to be rated as expected and capped at £50 and all calls after the capped amount to be rated a zero charge | VBC | MDN | 07-System Test | CMD | Drop1 | Design | Event Processing | MDN | MDN | Step 1
29 | TC_29_International SMS to Europe | Test Objective: To validate the ratring/capping functionality for International SMS Pre Condition: Apply £50 Capping offer | VFUK-Mobile\VBC\MDN_Drop1\Apply_£50Capping | Rate event with predefined SF/Tariff | Calls to be rated as expected and capped at £50 and all calls after the capped amount to be rated a zero charge | VBC | MDN | 07-System Test | CMD | Drop1 | Design | Event Processing | MDN | MDN | Step 1
30 | TC_30_International SMS to US | Test Objective: To validate the ratring/capping functionality for International SMS Pre Condition: Apply £50 Capping offer | VFUK-Mobile\VBC\MDN_Drop1\Apply_£50Capping | Rate event with predefined SF/Tariff | Calls to be rated as expected and capped at £50 and all calls after the capped amount to be rated a zero charge | VBC | MDN | 07-System Test | CMD | Drop1 | Design | Event Processing | MDN | MDN | Step 1
31 | TC_31_Roaming call from Europe to Canada | Test Objective: To validate the ratring/capping functionality for roaming voice calls Pre Condition: Apply £50 Capping offer | VFUK-Mobile\VBC\MDN_Drop1\Apply_£50Capping | Rate event with predefined SF/Tariff | Calls to be rated as expected and capped at £50 and all calls after the capped amount to be rated a zero charge | VBC | MDN | 07-System Test | CMD | Drop1 | Design | Event Processing | MDN | MDN | Step 1
32 | TC_32_Roaming call from Australia - In country | Test Objective: To validate the rating/capping functionality for roaming voice calls Pre Condition: Apply £50 Capping offer | VFUK-Mobile\VBC\MDN_Drop1\Apply_£50Capping | Rate event with predefined SF/Tariff | Calls to be rated as expected and capped at £50 and all calls after the capped amount to be rated a zero charge | VBC | MDN | 07-System Test | CMD | Drop1 | Design | Event Processing | MDN | MDN | Step 1
33 | TC_33_Roaming call from china to UK | Test Objective: To validate the ratring/capping functionality for roaming voice calls Pre Condition: Apply £50 Capping offer | VFUK-Mobile\VBC\MDN_Drop1\Apply_£50Capping | Rate event with predefined SF/Tariff | Calls to be rated as expected and capped at £50 and all calls after the capped amount to be rated a zero charge | VBC | MDN | 07-System Test | CMD | Drop1 | Design | Event Processing | MDN | MDN | Step 1
34 | TC_34_Roaming SMS in Canada | Test Objective: To validate the rating/capping functionality for roaming SMS Pre Condition: Apply £50 Capping offer | VFUK-Mobile\VBC\MDN_Drop1\Apply_£50Capping | Rate event with predefined SF/Tariff | Calls to be rated as expected and capped at £50 and all calls after the capped amount to be rated a zero charge | VBC | MDN | 07-System Test | CMD | Drop1 | Design | Event Processing | MDN | MDN | Step 1
35 | TC_35_Roaming Voice MT Calls | Test Objective: To validate the ratring/capping functionality for roaming MT calls Pre Condition: Apply £50 Capping offer | VFUK-Mobile\VBC\MDN_Drop1\Apply_£50Capping | Rate event with predefined SF/Tariff | Calls to be rated as expected and capped at £50 and all calls after the capped amount to be rated a zero charge | VBC | MDN | 07-System Test | CMD | Drop1 | Design | Event Processing | MDN | MDN | Step 1
36 | TC_36_NGN Calls | Test Objective: To validate the rating/capping functionality for NGN calls Pre Condition: Apply £50 Capping offer | VFUK-Mobile\VBC\MDN_Drop1\Apply_£50Capping | Rate event with predefined SF/Tariff | Calls to be rated as expected and capped at £50 and all calls after the capped amount to be rated a zero charge | VBC | MDN | 07-System Test | CMD | Drop1 | Design | Event Processing | MDN | MDN | Step 1
37 | TC_37_unitization 60/60 | Test Objective: To validate the ratring/capping functionality for a voice call with 60/60 unitisation Pre Condition: Apply £50 Capping offer | VFUK-Mobile\VBC\MDN_Drop1\Apply_£50Capping | Rate event with predefined SF/Tariff | Calls to be rated as expected and capped at £50 and all calls after the capped amount to be rated a zero charge | VBC | MDN | 07-System Test | CMD | Drop1 | Design | Event Processing | MDN | MDN | Step 1
38 | TC_38_unitization 60/1 | Test Objective: To validate the ratring/capping functionality for a voice call with 60/01 unitisation Pre Condition: Apply £50 Capping offer | VFUK-Mobile\VBC\MDN_Drop1\Apply_£50Capping | Rate event with predefined SF/Tariff | Calls to be rated as expected and capped at £50 and all calls after the capped amount to be rated a zero charge | VBC | MDN | 07-System Test | CMD | Drop1 | Design | Event Processing | MDN | MDN | Step 1
39 | TC_39_GPRS Domestic | Test Objective: To validate the ratring/capping functionality for domestic data calls Pre Condition: Apply £50 Capping offer | VFUK-Mobile\VBC\MDN_Drop1\Apply_£50Capping | Rate event with predefined SF/Tariff | Calls to be rated as expected and capped at £50 and all calls after the capped amount to be rated a zero charge | VBC | MDN | 07-System Test | CMD | Drop1 | Design | Event Processing | MDN | MDN | Step 1
40 | TC_40_GPRS ROAM | Test Objective: To validate the ratring/capping functionality for data roamig calls Pre Condition: Apply £50 Capping offer | VFUK-Mobile\VBC\MDN_Drop1\Apply_£50Capping | Rate event with predefined SF/Tariff | Calls to be rated as expected and capped at £50 and all calls after the capped amount to be rated a zero charge | VBC | MDN | 07-System Test | CMD | Drop1 | Design | Event Processing | MDN | MDN | Step 1

## Increase capping from 20£-50£
Test ID | Test Case | Test Objective | Path | Test Steps | Expected result | CRID | Responsible_App | Test_Level | Topic_Id | Version | Status | Story_Name | Detected_In_App | Involved_App | Test_Step_No
41 | TC_41_Increase capping from £20 to £50 at the start of the billing period | Test Objective: To test the behavior of capping after capping threshhold is increased. Pre Condition: Capping Offer available in Prod catalog Note : This will be achieved with Offer effective dates and NOT MDN actions | VFUK-Mobile\VBC\MDN_Drop1\Increase_capping_from_20£-50£ | Rate event with predefined SF/Tariff | Increase threshhold (i.e 50 pounds) to be applied at the start of the next month. Current bill month to be capped at £20 and events to be zero rated after £20. | VBC | MDN | 07-System Test | CMD | Drop1 | Design | Event Processing | MDN | MDN | Step 1
42 | TC_42_Increase capping from £20 to £50 at the Mid of the billing period | Test Objective: To test the behavior of capping after capping threshhold is increased. Pre Condition: Capping Offer available in Prod catalog Note : This will be achieved with Offer effective dates and NOT MDN actions | VFUK-Mobile\VBC\MDN_Drop1\Increase_capping_from_20£-50£ | Rate event with predefined SF/Tariff | Increase threshhold (i.e 50 pounds) to be applied at the start of the next month. Current bill month to be capped at £20 and events to be zero rated after £20. | VBC | MDN | 07-System Test | CMD | Drop1 | Design | Event Processing | MDN | MDN | Step 1
43 | TC_43_Increase capping from £20 to £50 at the end of the billing period | Test Objective: To test the behavior of capping after capping threshhold is increased. Pre Condition: Capping Offer available in Prod catalog Note : This will be achieved with Offer effective dates and NOT MDN actions | VFUK-Mobile\VBC\MDN_Drop1\Increase_capping_from_20£-50£ | Rate event with predefined SF/Tariff | Increase threshhold (i.e 50 pounds) to be applied at the start of the next month. Current bill month to be capped at £20 and events to be zero rated after £20. | VBC | MDN | 07-System Test | CMD | Drop1 | Design | Event Processing | MDN | MDN | Step 1

## Decreaese capping from 50£-20£
Test ID | Test Case | Test Objective | Path | Test Steps | expected result | CRID | Responsible_App | Test_Level | Topic_Id | Version | Status | Story_Name | Detected_In_App | Involved_App | Test_Step_No
44 | TC_44_Decrease capping from £50 to £20 at the start of the billing period | Test Objective: To test the behavior of capping after capping threshhold is decreased. Pre Condition: Capping Offer available in Prod catalog Note : This will be achieved with Offer effective dates and NOT MDN actions | VFUK-Mobile\VBC\MDN_Drop1\Decreaese_capping_from_50£-20£ | Rate event with predefined SF/Tariff | Decreased threshhold amount (i.e. £20 pounds) to be applied at the start of the next month. Current bill month to be capped at £50 and events to be zero rated after £50. | VBC | MDN | 07-System Test | CMD | Drop1 | Design | Event Processing | MDN | MDN | Step 1
45 | TC_45_Decrease capping from £50 to £20 at the Mid of the billing period | Test Objective: To test the behavior of capping after capping threshhold is decreased. Pre Condition: Capping Offer available in Prod catalog Note : This will be achieved with Offer effective dates and NOT MDN actions | VFUK-Mobile\VBC\MDN_Drop1\Decreaese_capping_from_50£-20£ | Rate event with predefined SF/Tariff | Decreased threshhold amount (i.e. £20 pounds) to be applied at the start of the next month. Current bill month to be capped at £50 and events to be zero rated after £50. | VBC | MDN | 07-System Test | CMD | Drop1 | Design | Event Processing | MDN | MDN | Step 1
46 | TC_46_Decrease capping from £50 to £20 at the end of the billing period | Test Objective: To test the behavior of capping after capping threshhold is decreased. Pre Condition: Capping Offer available in Prod catalog Note : This will be achieved with Offer effective dates and NOT MDN actions | VFUK-Mobile\VBC\MDN_Drop1\Decreaese_capping_from_50£-20£ | Rate event with predefined SF/Tariff | Decreased threshhold amount (i.e. £20 pounds) to be applied at the start of the next month. Current bill month to be capped at £50 and events to be zero rated after £50. | VBC | MDN | 07-System Test | CMD | Drop1 | Design | Event Processing | MDN | MDN | Step 1

## Apply Overide SOC Offer
Test ID | Test Case | Test Objective | Path | Test Steps | expected result | CRID | Responsible_App | Test_Level | Topic_Id | Version | Status | Story_Name | Detected_In_App | Involved_App | Test_Step_No
47 | TC_47_Apply Overide offer at the start of the billing period when threshhold has NOT exceeded | Test Objective: To test the behavior of Override offer/SOC when threshhold has not exceeded. Pre Condition: Capping/Override Offer available in Prod catalog | VFUK-Mobile\VBC\MDN_Drop1\Apply_Overide_SOC_Offer | Rate event with predefined SF/Tariff | No Zero rating to continue after the Override SOC Offer is effective | VBC | MDN | 07-System Test | CMD | Drop1 | Design | Event Processing | MDN | MDN | Step 1
48 | TC_48_Apply Overide offer at the end of the bill cycle month when threshhold is about to be exceeded | Test Objective: To test the behavior of Override offer after threshhold is exceeded Pre Condition: Capping/Override Offer available in Prod catalog | VFUK-Mobile\VBC\MDN_Drop1\Apply_Overide_SOC_Offer | Rate event with predefined SF/Tariff | No Zero rating to continue after the Override SOC Offer is effective | VBC | MDN | 07-System Test | CMD | Drop1 | Design | Event Processing | MDN | MDN | Step 1
49 | TC_49_Apply Overide offer at the Mid of the billing period when the threshold has exceeded | Test Objective: To test the behavior of Override offer after capping threshhold is about to be exceeded Pre Condition: Capping/Override Offer available in Prod catalog | VFUK-Mobile\VBC\MDN_Drop1\Apply_Overide_SOC_Offer | Rate event with predefined SF/Tariff | No Zero rating to continue after the Override SOC Offer is effective | VBC | MDN | 07-System Test | CMD | Drop1 | Design | Event Processing | MDN | MDN | Step 1

## Bundle Behavior
Test ID | Test Case | Test Objective | Path | Test Steps | Expected result | CRID | Responsible_App | Test_Level | Topic_Id | Version | Status | Story_Name | Detected_In_App | Involved_App | Test_Step_No
50 | TC_50_Apply capping offer along with the bundle offer that is still In Bundle | Test Objective: To validate capping behavior when IN Bundle Pre Condition: Capping/Bundle Offer available in Prod catalog | VFUK-Mobile\VBC\MDN_Drop1\Bundle_Behavior | Rate event with predefined SF/Tariff | Capping Not applied till subscriber is IN Bundle | VBC | MDN | 07-System Test | CMD | Drop1 | Design | Event Processing | MDN | MDN | Step 1
51 | TC_51_Apply capping offer along with the bundle offer is in between IN/OUT Bundle | Test Objective: To validate capping behavior when in between IN/OUTBundle Pre Condition: Capping/Bundle Offer available in Prod catalog | VFUK-Mobile\VBC\MDN_Drop1\Bundle_Behavior | Rate event with predefined SF/Tariff | Capping accumulation will accumulate only the Out of Bundle charges | VBC | MDN | 07-System Test | CMD | Drop1 | Design | Event Processing | MDN | MDN | Step 1
52 | TC_52_Apply capping offer along with the bundle offer Out of bundle | Test Objective: To validate capping behavior when Out of Bundle Pre Condition: Capping/Bundle Offer available in Prod catalog | VFUK-Mobile\VBC\MDN_Drop1\Bundle_Behavior | Rate event with predefined SF/Tariff | Capping accumulation will accumulate only the Out of Bundle charges | VBC | MDN | 07-System Test | CMD | Drop1 | Design | Event Processing | MDN | MDN | Step 1

## Remove capping
Test ID | Test Case | Test Objective | Path | Test Steps | Expected result | CRID | Responsible_App | Test_Level | Topic_Id | Version | Status | Story_Name | Detected_In_App | Involved_App | Test_Step_No
53 | TC_53_Remove capping Offer | Test Objective: To validate behavior after removal of caping offer Pre Condition: Customer has a valid capping offer | VFUK-Mobile\VBC\MDN_Drop1\Remove_capping_ | Rate event with predefined SF/Tariff after removal of capping offer | Event to be rated as expected after removal of capping offer is effective from. | VBC | MDN | 07-System Test | CMD | Drop1 | Design | Event Processing | MDN | MDN | Step 1

## Regression
Test ID | Test Case | Test Objective | Path | Test Steps | expected result | CRID | Responsible_App | Test_Level | Topic_Id | Version | Status | Story_Name | Detected_In_App | Involved_App | Test_Step_No
54 | TC_54_Domestic Voice without any capping offer | Test Objective: To Validate existing PP/offers rate as expected when No Capping Offer is applied Pre Condition: Customer has a valid PP (Offers) | VFUK-Mobile\VBC\MDN_Drop1\Regression | Rate event with predefined SF/Tariff | Events to be rated as expected as per the rate scheme of the package qulaified. No capping to be applied. | VBC | MDN | 07-System Test | CMD | Drop1 | Design | Regression | MDN | MDN | Step 1
55 | TC_55_Roam Voice without any capping offer | Test Objective: To Validate existing PP/offers rate as expected when No Capping Offer is applied Pre Condition: Customer has a valid PP (Offers) | VFUK-Mobile\VBC\MDN_Drop1\Regression | Rate event with predefined SF/Tariff | Events to be rated as expected as per the rate scheme of the package qulaified. No capping to be applied. | VBC | MDN | 07-System Test | CMD | Drop1 | Design | Regression | MDN | MDN | Step 1
56 | TC_56_International Voice without any capping offer | Test Objective: To Validate existing PP/offers rate as expected when No Capping Offer is applied Pre Condition: Customer has a valid PP (Offers) | VFUK-Mobile\VBC\MDN_Drop1\Regression | Rate event with predefined SF/Tariff | Events to be rated as expected as per the rate scheme of the package qulaified. No capping to be applied. | VBC | MDN | 07-System Test | CMD | Drop1 | Design | Regression | MDN | MDN | Step 1
57 | TC_57_SMS Domestic without any capping offer | Test Objective: To Validate existing PP/offers rate as expected when No Capping Offer is applied Pre Condition: Customer has a valid PP (Offers) | VFUK-Mobile\VBC\MDN_Drop1\Regression | Rate event with predefined SF/Tariff | Events to be rated as expected as per the rate scheme of the package qulaified. No capping to be applied. | VBC | MDN | 07-System Test | CMD | Drop1 | Design | Regression | MDN | MDN | Step 1
58 | TC_58_Roam SMS from EU or ROW without any capping offer | Test Objective: To Validate existing PP/offers rate as expected when No Capping Offer is applied Pre Condition: Customer has a valid PP (Offers) | VFUK-Mobile\VBC\MDN_Drop1\Regression | Rate event with predefined SF/Tariff | Events to be rated as expected as per the rate scheme of the package qulaified. No capping to be applied. | VBC | MDN | 07-System Test | CMD | Drop1 | Design | Regression | MDN | MDN | Step 1
59 | TC_59_GPRS Domestic without any capping offer | Test Objective: To Validate existing PP/offers rate as expected when No Capping Offer is applied Pre Condition: Customer has a valid PP (Offers) | VFUK-Mobile\VBC\MDN_Drop1\Regression | Rate event with predefined SF/Tariff | Events to be rated as expected as per the rate scheme of the package qulaified. No capping to be applied. | VBC | MDN | 07-System Test | CMD | Drop1 | Design | Regression | MDN | MDN | Step 1
60 | TC_60_GPRS Roaming without any capping offer | Test Objective: To Validate existing PP/offers rate as expected when No Capping Offer is applied Pre Condition: Customer has a valid PP (Offers) | VFUK-Mobile\VBC\MDN_Drop1\Regression | Rate event with predefined SF/Tariff | Events to be rated as expected as per the rate scheme of the package qulaified. No capping to be applied. | VBC | MDN | 07-System Test | CMD | Drop1 | Design | Regression | MDN | MDN | Step 1
61 | TC_61_MPAY calls with out any capping offer | Test Objective: To Validate existing PP/offers rate as expected when No Capping Offer is applied Pre Condition: Customer has a valid PP (Offers) | VFUK-Mobile\VBC\MDN_Drop1\Regression | Rate event with predefined SF/Tariff | Events to be rated as expected as per the rate scheme of the package qulaified. No capping to be applied. | VBC | MDN | 07-System Test | CMD | Drop1 | Design | Regression | MDN | MDN | Step 1

## document control
Zero Rating Functionality
Revision History
Version | Date | Author | Change Summary
0.1 | 2018-08-08 | Firasat Shukla | First draft
Distribution List
Name | Position | Email

## document control (2)
Zero Rating Functionality
Revision History
Version | Date | Author | Change Summary
0.1 | 2018-08-08 | Firasat Shukla | First draft
Distribution List
Name | Position | Email